## app
|  | DOST- PHILIPPINE TEXTILE RESEARCH INSTITUTE - Indicative Annual Procurement Plan for FY 2023 | [11 empty] | Department of Budget and Management Procurement Monitoring Report as of month/day/2006
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? (Yes/No) | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (brief description of Project) | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [8 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Advertisement/Posting of IB/REI | Submission/Opening of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  | Pre-Proc Conf | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Delivery/ Accept
100000100001000 | Travel-Local | PTRI | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 22000 | 22000 |  | indefinite dates, venues, frequency of activities
100000100002000 | Travel-Local | PTRI | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 23000 | 23000 |  | indefinite dates, venues, frequency of activities
310100100001000 | Travel-Local | PTRI | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 294000 | 294000 |  | indefinite dates, venues, frequency of activities
310200100001000 | Travel-Local | PTRI | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 74000 | 74000 |  | indefinite dates, venues, frequency of activities
310300100001000 | Travel-Local | PTRI | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 318000 | 318000 |  | indefinite dates, venues, frequency of activities
100000100002000 | Training Expense | PTRI | NO |  | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 23000 | 23000 |  | indefinite dates, venues, frequency of activities
310100100001000 | Training Expense | PTRI | NO |  | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 200000 | 200000 |  | indefinite dates, venues, frequency of activities
310200100001000 | Training Expense | PTRI | NO |  | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 850000 | 850000 |  | indefinite dates, venues, frequency of activities
310300100001000 | Training Expense | PTRI | NO |  | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 28000 | 28000 |  | indefinite dates, venues, frequency of activities
100000100001000 | Office Supplies Expense | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 584000 | 584000 |  | indefinite dates, venues, frequency of activities
100000100002000 | Office Supplies Expense | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 7000 | 7000 |  | indefinite dates, venues, frequency of activities
310100100001000 | Office Supplies Expense | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 149000 | 149000 |  | indefinite dates, venues, frequency of activities
310200100001000 | Office Supplies Expense | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 256000 | 256000 |  | indefinite dates, venues, frequency of activities
310300100001000 | Office Supplies Expense | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 438000 | 438000 |  | indefinite dates, venues, frequency of activities
100000100001000 | Accountable Forms Expense | PTRI | NO | NP-53.5 Agency-to-Agency | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 50000 | 50000 |  | National Printing Office
100000100001000 | Medical, Dental and Laboratory Supplies Expenses | PTRI | NO | Shopping/NP-53.9 Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 50000 | 50000 |  | indefinite dates, venues, frequency of activities
310100100001000 | Medical, Dental and Laboratory Supplies Expenses | PTRI | NO | Shopping/NP-53.9 Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 729000 | 729000 |  | indefinite dates, venues, frequency of activities
310200100001000 | Medical, Dental and Laboratory Supplies Expenses | PTRI | NO | Shopping/NP-53.9 Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 6324000 | 6324000 |  | indefinite dates, venues, frequency of activities
100000100001000 | Fuel, Oil and Lubricants Expense | PTRI | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 813000 | 813000 |  | Contract Agreement with Gasoline Station
310100100001000 | Fuel, Oil and Lubricants Expense | PTRI | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 77000 | 77000 |  | Contract Agreement with Gasoline Station
310200100001000 | Fuel, Oil and Lubricants Expense | PTRI | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 63000 | 63000 |  | Contract Agreement with Gasoline Station
310300100001000 | Fuel, Oil and Lubricants Expense | PTRI | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 40000 | 40000 |  | Contract Agreement with Gasoline Station
100000100001000 | Other Supplies and Materials Expenses | PTRI | NO | Shopping/NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 253000 | 253000 |  | indefinite dates, venues, frequency of activities
10000010002000 | Other Supplies and Materials Expenses | PTRI | NO | Shopping/NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 10000 | 10000 |  | indefinite dates, venues, frequency of activities
310100100001000 | Other Supplies and Materials Expenses | PTRI | NO | Shopping/NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 939000 | 939000 |  | indefinite dates, venues, frequency of activities
310200100001000 | Other Supplies and Materials Expenses | PTRI | NO | Shopping/NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 96000 | 96000 |  | indefinite dates, venues, frequency of activities
310300100001000 | Other Supplies and Materials Expenses | PTRI | NO | Shopping/NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 40000 | 40000 |  | indefinite dates, venues, frequency of activities
100000100001000 | Water Expenses | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 347000 | 347000 |  | Monthly Consumption - Maynilad
310100100001000 | Water Expenses | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 145000 | 145000 |  | Monthly Consumption - Maynilad
310200100001000 | Water Expenses | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 616000 | 616000 |  | Monthly Consumption - Maynilad
310300100001000 | Water Expenses | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 54000 | 54000 |  | Monthly Consumption - Maynilad
100000100001000 | Electricity Expenses | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 3988000 | 3988000 |  | Monthly Consumption - Meralco
310100100001000 | Electricity Expenses | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 808000 | 808000 |  | Monthly Consumption - Meralco
310200100001000 | Electricity Expenses | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 2562000 | 2562000 |  | Monthly Consumption - Meralco
310300100001000 | Electricity Expenses | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 722000 | 722000 |  | Monthly Consumption - Meralco
310200100001000 | Gas/Heating Expenses | PTRI | NO | Shopping/Direct Contracting | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 40000 | 40000 |  | Contract Agreement with Diamond Gas House Corp.
100000100001000 | Postage and Courier Services | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 12000 | 12000 |  | indefinite dates, venues, frequency of activities
310100100001000 | Postage and Courier Services | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 12000 | 12000 |  | indefinite dates, venues, frequency of activities
310200100001000 | Postage and Courier Services | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 4000 | 4000 |  | indefinite dates, venues, frequency of activities
310300100001000 | Postage and Courier Services | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 46000 | 46000 |  | indefinite dates, venues, frequency of activities
100000100001000 | Telephone Expenses - Mobile | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 12000 | 12000 |  | CELL CARDS (indefinite dates, venues, frequency of activities)
310100100001000 | Telephone Expenses - Mobile | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 22000 | 22000 |  | CELL CARDS (indefinite dates, venues, frequency of activities)
310200100001000 | Telephone Expenses - Mobile | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 52000 | 52000 |  | CELL CARDS (indefinite dates, venues, frequency of activities)
310300100001000 | Telephone Expenses - Mobile | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 8000 | 8000 |  | CELL CARDS (indefinite dates, venues, frequency of activities)
100000100001000 | Telephone Expenses - Landline | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 190000 | 190000 |  | PLDT
310100100001000 | Telephone Expenses - Landline | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 40000 | 40000 |  | PLDT
310200100001000 | Telephone Expenses - Landline | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 32000 | 32000 |  | PLDT
310300100001000 | Telephone Expenses - Landline | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 108000 | 108000 |  | PLDT
310100100001000 | Internet Subscription Expenses | PTRI | NO | Direct Contracting/NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 50000 | 50000 |  | Monthly ISP subscription
310200100001000 | Internet Subscription Expenses | PTRI | NO | Direct Contracting/NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 5000 | 5000 |  | Monthly ISP subscription
310300100001000 | Internet Subscription Expenses | PTRI | NO | Direct Contracting/NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 106000 | 106000 |  | Monthly ISP subscription
100000100002000 | Awards/Rewards Expenses | PTRI | NO | [5 empty] | GoP | 55000 | 55000 |  | PRAISE Incidental Expenses
100000100002000 | Prizes | PTRI | NO | [5 empty] | GoP | 36000 | 36000 |  | PTRI Employees Incentive Award
100000100001000 | Extraordinary and Miscellaneous Expenses | PTRI | NO | [5 empty] | GoP | 136000 | 136000 |  | provision for PTRI Director
100000100001000 | Legal Services | PTRI | NO | [5 empty] | GoP | 60000 | 60000 |  | provision for Legal Services (Notary)
310200100001000 | Legal Services | PTRI | NO | [5 empty] | GoP | 2000 | 2000 |  | provision for Legal Services (Notary)
310300100001000 | Legal Services | PTRI | NO | [5 empty] | GoP | 2000 | 2000 |  | provision for Legal Services (Notary)
310200100001000 | Auditing Services | PTRI | YES | [5 empty] | GoP | 20000 | 20000 |  | COA
310200100001000 | Auditing Services | PTRI | YES | [5 empty] | GoP | 300000 | 300000 |  | COA
100000100001000 | Other Professional Services | PTRI | YES | Competitive Bidding | Q4 2022 | Q4 2022 | Q1 2023 | Q1 2023 | GoP | 3006000 | 3006000
310100100001000 | Other Professional Services | PTRI | YES | Competitive Bidding | Q4 2022 | Q4 2022 | Q1 2023 | Q1 2023 | GoP | 2918000 | 2918000
310200100001000 | Other Professional Services | PTRI | YES | Competitive Bidding | Q4 2022 | Q4 2022 | Q1 2023 | Q1 2023 | GoP | 8630000 | 8630000
310300100001000 | Other Professional Services | PTRI | YES | Competitive Bidding | Q4 2022 | Q4 2022 | Q1 2023 | Q1 2023 | GoP | 3125000 | 3125000
100000100001000 | Janitorial Services | PTRI | NO | [5 empty] | GoP | 1706000 | 1706000 |  | 2nd yr of 3-year Contract with CBII Philippines
310100100001000 | Janitorial Services | PTRI | NO | [5 empty] | GoP | 138000 | 138000 |  | 2nd yr of 3-year Contract with CBII Philippines
100000100001000 | Security Services | PTRI | YES | Competitive Bidding | Q4 2022 | Q4 2022 | Q1 2023 | Q1 2023 | GoP | 2319000 | 2319000 |  | To be included in DOST-Central Office Early Procurement
310100100001000 | Security Services | PTRI | YES | Competitive Bidding | Q4 2022 | Q4 2022 | Q1 2023 | Q1 2023 | GoP | 520000 | 520000 |  | To be included in DOST-Central Office Early Procurement
100000100001000 | Other General Services | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 28000 | 28000 |  | indefinite dates, venues, frequency of activities
100000100001000 | Repair and Maintenance - Building | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 100000 | 100000 |  | indefinite dates, venues, frequency of activities
310100100001000 | Repair and Maintenance - Building | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 25000 | 25000 |  | indefinite dates, venues, frequency of activities
310200100001000 | Repair and Maintenance - Building | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 600000 | 600000 |  | indefinite dates, venues, frequency of activities
100000100001000 | Repair and Maintenance - Other Structures | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 10000 | 10000 |  | indefinite dates, venues, frequency of activities
310200100001000 | Repair and Maintenance - Other Structures | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 40000 | 40000 |  | indefinite dates, venues, frequency of activities
100000100001000 | Repair and Maintenance - Office Equipment | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 50000 | 50000 |  | indefinite dates, venues, frequency of activities
310100100001000 | Repair and Maintenance - Technical and Scientific Equipment | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 264000 | 264000 |  | indefinite dates, venues, frequency of activities
310200100001000 | Repair and Maintenance - Technical and Scientific Equipment | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 3510000 | 3510000 |  | indefinite dates, venues, frequency of activities
310300100001000 | Repair and Maintenance - Technical and Scientific Equipment | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 100000 | 100000 |  | indefinite dates, venues, frequency of activities
100000100001000 | Repair and Maintenance- Motor Vehicles | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 200000 | 200000 |  | indefinite dates, venues, frequency of activities
310100100001000 | Repair and Maintenance- Motor Vehicles | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 20000 | 20000 |  | indefinite dates, venues, frequency of activities
310200100001000 | Repair and Maintenance- Furniture and Fixtures | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 426000 | 426000 |  | indefinite dates, venues, frequency of activities
310300100001000 | Repair and Maintenance- Furniture and Fixtures | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 96000 | 96000 |  | indefinite dates, venues, frequency of activities
310100100001000 | Repair and Maintenance - Leased Assets Improvement (Land) | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 80000 | 80000 |  | indefinite dates, venues, frequency of activities
100000100001000 | Taxes, Duties & Licenses | PTRI | NO | Direct Contracting/NP-53.5 Agency-to-Agency | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 58000 | 58000 |  | Custom Duties/Taxes, Indefinite dates, frequency of activities
310200100001000 | Taxes, Duties & Licenses | PTRI | NO | Direct Contracting/NP-53.5 Agency-to-Agency | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 55000 | 55000 |  | Custom Duties/Taxes, Indefinite dates, frequency of activities
100000100001000 | Fidelity Bond Premiums | PTRI | NO | NP-53.5 Agency-to-Agency | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 408000 | 408000 |  | Fidelity Bond of employees
310100100001000 | Fidelity Bond Premiums | PTRI | NO | NP-53.5 Agency-to-Agency | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 2000 | 2000 |  | Fidelity Bond of employees
310200100001000 | Fidelity Bond Premiums | PTRI | NO | NP-53.5 Agency-to-Agency | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 10000 | 10000 |  | Fidelity Bond of employees
310300100001000 | Fidelity Bond Premiums | PTRI | NO | NP-53.5 Agency-to-Agency | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 8000 | 8000 |  | Fidelity Bond of employees
100000100001000 | Insurance Expenses | PTRI | NO | NP-53.5 Agency-to-Agency | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 1932000 | 1932000 |  | GSIS Insurance/ LTO Registration
310100100001000 | Insurance Expenses | PTRI | NO | NP-53.5 Agency-to-Agency | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 9000 | 9000 |  | GSIS Insurance/ LTO Registration
310200100001000 | Insurance Expenses | PTRI | NO | NP-53.5 Agency-to-Agency | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 500000 | 500000 |  | GSIS Insurance/ LTO Registration
100000100001000 | Advertising Expenses | PTRI | NO | Direct Contracting/Shopping/NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 11000 | 11000 |  | Advertisement of vacant position & Posting of ITB to newspaper
310200100001000 | Advertising Expenses | PTRI | NO | Direct Contracting/Shopping/NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 403000 | 403000 |  | Advertisement of vacant position & Posting of ITB to newspaper
310300100001000 | Advertising Expenses | PTRI | NO | Direct Contracting/Shopping/NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 20000 | 20000 |  | Advertisement of vacant position & Posting of ITB to newspaper
100000100001000 | Printing and Publication Expenses | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 16000 | 16000 |  | Printing of PTRI Annual Report/Bulletin, etc.
310100100001000 | Printing and Publication Expenses | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 1000 | 1000 |  | Printing of PTRI Annual Report/Bulletin, etc.
310200100001000 | Printing and Publication Expenses | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 25000 | 25000 |  | Printing of PTRI Annual Report/Bulletin, etc.
310300100001000 | Printing and Publication Expenses | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 134000 | 134000 |  | Printing of PTRI Annual Report/Bulletin, etc.
100000100001000 | Representation Expenses | PTRI | NO | Shopping/NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 30000 | 30000 |  | Office of the Director
310100100001000 | Representation Expenses | PTRI | NO | Shopping/NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 74000 | 74000 |  | Office of the Director
310200100001000 | Representation Expenses | PTRI | NO | Shopping/NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 130000 | 130000 |  | Office of the Director
310300100001000 | Representation Expenses | PTRI | NO | Shopping/NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 24000 | 24000 |  | PICTS
100000100001000 | Transportation and Delivery Expenses | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 2000 | 2000 |  | indefinite dates, venues, frequency of activities
310100100001000 | Transportation and Delivery Expenses | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 131000 | 131000 |  | indefinite dates, venues, frequency of activities
310200100001000 | Transportation and Delivery Expenses | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 63000 | 63000 |  | indefinite dates, venues, frequency of activities
310300100001000 | Transportation and Delivery Expenses | PTRI | NO | NP-53.9 - Small Value Procurement | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 20000 | 20000 |  | indefinite dates, venues, frequency of activities
310100100001000 | Rent/Lease Expenses - Land | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 18000 | 18000 |  | NHA Lease to TCMO
100000100001000 | Other Subscription Expenses | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 3000 | 3000 |  | indefinite dates, venues, frequency of activities
310200100001000 | Other Subscription Expenses | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 2000 | 2000 |  | indefinite dates, venues, frequency of activities
310300100001000 | Other Subscription Expenses | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 42000 | 42000 |  | indefinite dates, venues, frequency of activities
310300100001000 | Other Subscription Expenses | PTRI | NO | Direct Contracting | N/A | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 42000 | 42000 |  | indefinite dates, venues, frequency of activities
100000100001000 | Other Maintenance and Operating Expenses | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 1000 | 1000 |  | indefinite dates, venues, frequency of activities
310300100001000 | Other Maintenance and Operating Expenses | PTRI | NO | Shopping | Q1 to Q4 | N/A | Q1 to Q4 | Q1 to Q4 | GoP | 20000 | 20000 |  | indefinite dates, venues, frequency of activities
310100200017000 | Office Building | PTRI | YES | Competitive Bidding | Q3 2022 | Q4 2022 | Q1 2022 | Q1 2022 | GoP | 24250000 |  | 24250000 | Rehabilitation and Retrofitting of the Natural Fiber Processing Center
[9 empty] | Total | 79697000 | 55447000 | 24250000
Prepared by: | Recommending Approval by: | [10 empty] | Approved by:
| Bids and Awards Committee | [10 empty] | Head of Procuring Entity
MARILOU G. AGUSTIN | JULIUS L. LEAÑO, JR., Ph.D. |  | CORAZON I. TAPULGO |  | DANIEL LEON J. LAVIN |  |  |  | MARNIE B. DONES |  |  | CORAZON I. TAPULGO
Head, BAC Secretariat | Chairperson |  | Vice Chairperson |  | Member |  |  |  | Member |  |  | Officer-In-Charge, Office of the Director
[5 empty] | JENNELI E. CAYA |  |  |  | MERLITA R. ODI
[5 empty] | Member |  |  |  | Member

## how_to_fill_out-definitions
| GUIDE TO PREPARE APP | APP COLUMN HEADER/S
STEP 1 | In the Code column, kindly indicate the PAP Code. Please refer to the code indicated in the technical budget posted in the DBM website. For GOCCs and LGUs, indicate the procuring entity's internal numbering system. | Code (PAP)
STEP 2 | For the Procurement Project column, please align descriptions of program/projects with budget documents and ensure clarity and accuracy in describing each procurement program/project. | Procurement Project
STEP 3 | For PMO/End-User, please indicate the PMO/End-User unit who will implement/utilize the procurement program/project. Multiple end-user units are allowed only if the procurement activity was consolidated by the BAC to procure requirements of the end-user units. | PMO/End-User
STEP 4 | For Mode of Procurement and Schedule for Each Procurement Activity, all modes of procurement are available as a dropdown list and requirements for a specific schedule for Ads/Post of IB/REI, Sub/Open of Bids, Notice of Award, and/or Contract Signing are automatically identified thru the MS Excel formula. Note that for Foreign-funded procurement, please use Others - Foreign-funded procurement as the Mode of Procurement. Kindly indicate a specific period (dates, month, quarter) when each Procurement Activity will be done. Please refer to our website: http://www.gppb.gov.ph/timelines/timelines.htm for the specific periods for each activity. Note: For SVP, IB/REI is similar to RFQ. Ads/Post of IB/REI for Shopping 52.1(b) and NP-SVP (53.9) needs to be posted in PhilGEPS for ABCs above 50k. Notice of Award posting in PhilGEPS is mandatory for all Alternative Modes only for ABCs above 50k. | Mode of Procurement | Schedule for Each Procurement Activity
|  |  | Ads/Post of IB/REI | Sub/Open of Bids | Notice of Award | Contract Signing
STEP 5 | For Source of Funds, a dropdown list is available. If the Source of Funds the PE will use is not included, please indicate "Others" and specify under the Remarks column. | Source of Funds
STEP 6 | For Estimated Budget (PhP), kindly fill out either MOOE or CO columns only. Total ABC column is not editable, but will automatically compute for the total MOOE and CO components of the project. This breakdown is needed for tracking purposes. Finally, please ensure that amounts indicated are aligned with budget documents. | Estimated Budget (PhP)
STEP 7 | Before submission to the GPPB, ensure that the Head of the Procuring Entity (HoPE) approves/signs the APP.
GENERAL INFORMATION
#1 | All Cells with Fill Color Orange needs to be filled out by the Agency. This is a visual reminder of blank or improperly filled out cells.
#2 | To ensure that automated indicator which procurement activity needs to be filled out with specific periods, PE must copy entire Excel row with the mode of procurement for the specific procurement program/project and paste on the last sample row "Negotiated Procurement-53.13" in the template.
#3 | If PE wishes to edit formatting and design of borders, fonts, among others of the APP template, it is suggested to utilize the automated formulas in the template before copying contents and reformatting.
#4 | Per Section of 3.1.1 of DBM Circular No. 2015-7, the Approved Budget for the Contract (ABC) shall be “[t]he amount reflected in the MYOA”. Hence, the ABC in the Annual Procurement Plan (APP) shall be the full amount stated in the MYOA with remarks added on how much will be actually disbursed for that particular fiscal year. Moreover, the Procurement Monitoring Report (PMR) should also reflect full amount in the MYOA if the entire contract was awarded within the fiscal year. Thus, for succeeding years, actual disbursements from the MYOA need not be reflected in the APPs and PMRs, unless current contract with MYOA is terminated and a new procurement activity is undertaken.
DEFINITIONS
1. PROGRAM (BESF)– A homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, for the basic maintenance of the agency’s administrative operations or for the provisions of staff support to the agency’s administrative operations or for the provisions of staff support to the agency’s line functions.
2. PROJECT (BESF)– Special agency undertakings which are to be carried out within a definite time frame and which are intended to result in some pre-determined measure of goods and services.
3. PMO/End User - Unit as proponent of program or project
4. Mode of Procurement - Competitive Bidding and Alternative Methods including: selective bidding, direct contracting, repeat order, shopping, and negotiated procurement.
5. Schedule for Each Procurement Activity - Major procurement activities (advertising/posting; submission and receipt/Opening of bids; award of contract; contract signing).
6. Source of Funds - Whether GoP, Foreign Assisted or Special Purpose Fund
7. Estimated Budget - Agency approved estimate of project/program costs
8. Remarks - brief description of program or project