## pmr (as of 6.30)
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | Philippine Textile Research Institute Procurement Monitoring Report as of June 30, 2021
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| RFQ No. 005-21 (R) 1 Unit Impact Penetration Tester, Type I | [19 empty] | TSD-Chem | NO | NP-53.9 - Small Value Procurement | N/A | Jan. 18-25, 2021 | N/A | N/A | N/A | N/A | N/A | Feb. 19,2021 | 2021-03-30 | 2021-03-30 | Apr. 29,2021 | 2021-05-28 | 2021-05-28 | GoP | 100000 | 100000 | 0 | 100000 | 100000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 062-21 Three (3) Packs Rubber Diaphragm | [19 empty] | TSD-Phy | NO | Direct Contracting | N/A | Feb. 2-9, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | Apr. 14, 2021 | Apr. 14, 2021 | Apr. 14, 2021 | 2021-05-21 | 2021-05-21 | GoP | 97500 | 97500 | 0 | 95000 | 95000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 063-21 One (1) Set Jaw Inserts, Vulkollan Smooth | [19 empty] | TSD-Phy | NO | Direct Contracting | N/A | Feb. 2-9, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-03 | 2021-03-03 | 2021-03-03 | Apr. 29, 2021 | Apr. 29, 2021 | GoP | 180000 | 180000 | 0 | 176988.12 | 176988.12 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 078-21 Ten (10) Boxes, Multifiber Standard Adjacent Fabric ISO DW | [19 empty] | TSD-Chem | NO | Direct Contracting | N/A | Feb. 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-03-09 | 2021-03-09 | Apr. 26, 2021 | Apr. 26, 2021 | 2021-05-28 | 2021-05-28 | GoP | 57000 | 57000 | 0 | 54800 | 54800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 081-21 One (1) Lot Multifiber Fabric FA #10 | [19 empty] | TSD-Chem | NO | Direct Contracting | N/A | Feb. 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | Feb. 19, 2021 | Feb. 19, 2021 | Apr. 20, 2021 | Apr. 20, 2021 | 2021-05-28 | 2021-05-28 | GoP | 200000 | 200000 | 0 | 174200 | 174200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 082-21 Repair and Maintenance of Precision Air Conditioning System | [19 empty] | TSD-Chem | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 8-15, 2021 | N/A | N/A | N/A | N/A | 2021-03-15 | 2021-03-11 | 2021-03-11 | Apr. 26, 2021 | Apr. 26, 2021 | 2021-05-10 | 2021-05-10 | GoP | 230000 | 230000 | 0 | 200000 | 200000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 110-21 One (1) Lot Fabrication amd Installation of Customized Office Workstation | [19 empty] | OD-TIPS | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 22-Mar. 1, 2021 | N/A | N/A | N/A | N/A | 2021-03-15 | 2021-03-19 | 2021-03-19 | Apr. 29, 2021 | Apr. 29, 2021 | 2021-05-14 | 2021-05-14 | GoP | 245000 | 245000 | 0 | 200000 | 200000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 532-20 One (1) Unit Firewall License for Network Module and Web Module / One (1) Unit Sophos SG210 Enterprise Guard - 3 years subscription | [19 empty] | PICTS | NO | Shopping | N/A | Dec. 4, - 11, 2020 | N/A | N/A | N/A | N/A | 2021-03-01 | Mar. 4, 2021 | Mar. 4, 2021 | Mar. 30, 2021 | Mar. 30, 2021 | Apr. 7, 2021 | Apr. 7, 2021 | GoP | 300000 | 300000 | 0 | 178000 | 178000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 1409500
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 1178988.12
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 230511.88
0N-GOING PROCUREMENT ACTIVITIES
| RFQ No. 002-21 (R) 1 Lot Top Loading Balance / Digital Floor Scale | [19 empty] | RDD-NFUS | NO | Shopping | N/A | Jan. 18-25, 2021 | N/A | N/A | N/A | N/A | N/A | Apr. 8, 2021 | Apr. 8, 2021 | Apr. 29,2021 | Apr. 29, 2021 |  |  | GoP | 250000 | 250000 | 0 | 175000 | 175000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 003-21 (R) One (1) Lot Moisture Analyzer | [19 empty] | RDD-NFUS | NO | Shopping | N/A | Jan. 16-21, 2021 | N/A | N/A | N/A | N/A | N/A | Apr. 6, 2021 | Apr. 6,2021 | May 3, 2021 | 2021-05-03 |  |  | GoP | 200000 | 200000 | 0 | 160000 | 160000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 004-21 (R) 2 Lots Vacuum Pump | [19 empty] | RDD-NFUS | NO | Shopping | N/A | Jan. 18-25, 2021 | N/A | N/A | N/A | N/A | Feb. 15, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 200000 | 200000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed Bid
| RFQ No. 006-21 (R) 2 Units ATP Meter | [19 empty] | TSD-Chem | NO | NP-53.9 - Small Value Procurement | N/A | Jan. 18-25, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 200000 | 200000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed Bid
| RFQ No. 007-21 (R) 3 Units Handheld Label Maker | [19 empty] | TSD-Chem | NO | Shopping | N/A | Jan. 18-25, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-03-25 | May 4, 2021 | May 4, 2021 | May 4, 2021 |  |  | GoP | 54000 | 54000 | 0 | 42109 | 42109 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 013-21 Network Attached Storage (NAS) | [19 empty] | OD-PICTS | NO | Shopping | N/A | Jan. 25-Feb. 1, 2021 | N/A | N/A | N/A | N/A | 2021-03-11 | 2021-03-26 | 2021-03-26 |  | Apr. 23, 2021 |  |  | GoP | 90000 | 90000 | 0 | 55440 | 55440 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 649-20 1 Unit Virtual Meetings Application / 1 unit Virtual Video Webinar Application | [19 empty] | OD-PICTS | NO | Shopping | N/A | Jan. 13-18, 2021 | N/A | N/A | N/A | N/A | N/A | [13 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RDQ No. 641-20 One (1) Unit Biological Safety Cabinet | [20 empty] | NO | NP-53.9 - Small Value Procurement | N/A | Jan. 13-20, 2021 | N/A | N/A | N/A | N/A | N/A | Feb. 17, 2021 | Feb. 17, 2021 |  |  |  |  | GoP | 1000000 | 1000000 | 0 | 675800 | 675800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 061-21 One (1) Lot Replacement of Defective Condenser Fan Motor | [19 empty] | TSD-Phy | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 2-9, 2021 | N/A | N/A | N/A | N/A | Apr. 23, 2021 | Apr. 28, 2021 | Apr. 28, 2021 |  | June 14, 2021 |  |  | GoP | 130000 | 130000 | 0 | 120000 | 120000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 064-21 One (1) Lot 30Mbps Internet Services (Burstable) | [19 empty] | OD-PICTS | NO | Shopping | N/A | Feb. 2-9, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 264000 | 264000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 065-21 Three (3) Units 24-Port Gigabit Managed Switch | [19 empty] | OD-PICTS | NO | Shopping | N/A | Feb. 2-9, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-03-05 | 2021-03-05 |  |  |  |  | GoP | 69000 | 69000 | 0 | 58125 | 58125 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 071-21 Five-Hundred (500) kgs, Cotton Fibers | [19 empty] | TSD-MCPU | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 65000 | 65000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 074-21 One (1) Lot Various IT Accessories and Peripherals | [19 empty] | TSD-MCPU | NO | Shopping | N/A | Feb. 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 104848 | 104848 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed Bid
| RFQ No. 079-21 Forty (40) pieces Glass Gooch Crucible, Low Form | [19 empty] | TSD-Chem | NO | Shopping | N/A | Feb. 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | Feb. 19, 2021 | Feb. 19, 2021 |  |  |  |  | GoP | 54000 | 54000 | 0 | 53000 | 53000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 086-21 One (1) Unit Impact Penetration Tester | [19 empty] | TSD-Chem | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 8-15, 2021 | N/A | N/A | N/A | N/A | N/A | Feb. 19, 2021 | Feb. 19, 2021 |  | 2021-03-30 |  |  | GoP | 100000 | 100000 | 0 | 100000 | 100000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 091-21 Thirty-Five (35) Units Application Software for Home and Business 2019 (Word, Excel, Powerpoint, Outlook) | [19 empty] | OD-PICTS | NO | Shopping | N/A | Feb. 8-15, 2021 | N/A | N/A | N/A | N/A | 2021-03-11 | 2021-03-25 | 2021-03-25 |  | Apr. 20, 2021 |  |  | GoP | 700000 | 700000 | 0 | 343000 | 343000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 092-21 Ten (10) Units Laser / Laserjet Colored Printer | [19 empty] | OD-PICTS | NO | Shopping | N/A | Feb. 8-15, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 200000 | 200000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed Bid
| RFQ No. 099-21 One (1) Lot Various Fabrics | [19 empty] | RDD-CDABUS | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 11-18, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 72000 | 72000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 100-21 One (1) Lot Analytical Balance | [19 empty] | RDD-NFUS | NO | Shopping | N/A | Feb. 11-18, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-03-16 | 2021-03-16 |  | Apr. 23, 2021 |  |  | GoP | 197500 | 197500 | 0 | 145000 | 145000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 102-21 Two (2) Units Autoclave | [19 empty] | TSD-Chem | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 18-26, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 800000 | 800000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 103-21 Two (2) Units Distilling Apparatus | [19 empty] | TSD-Chem | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 18-26, 2021 | N/A | N/A | N/A | N/A | Apr. 23, 2021 | Apr. 28, 2021 | Apr. 28, 2021 |  |  |  |  | GoP | 900000 | 900000 | 0 | 680000 | 680000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failure
| RFQ No. 101-21 One (1) Unit Trinocular Microscope | [19 empty] | TSD-Chem | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 18-26, 2021 | N/A | N/A | N/A | N/A | Apr. 23, 2021 | Apr. 28, 2021 | Apr. 28, 2021 |  | June 9, 2021 |  |  | GoP | 100000 | 100000 | 0 | 90000 | 90000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 106-21 One (1) Unit Photoshop CC License / One (1) Unit Indesign CC License | [19 empty] | OD-PICTS | NO | Shopping | N/A | Feb. 18-26, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-03-05 | 2021-03-05 |  |  |  |  | GoP | 60000 | 60000 | 0 | 44000 | 44000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 107-21 AATCC Blue Wool Lightfastness Standards/Blue Wool Reference/Standard of Fading (5 & 20 AATCC Fading Unit) | [19 empty] | TSD-Physical | NO | Shopping | N/A | Feb. 18-22, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 70000 | 70000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed bid
| FRQ No. 109-21 One (1) Lot Security Cameras with Labor and Installation | [19 empty] | FAD-BTS | NO | Shopping | N/A | Feb. 22-Mar. 1, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 90000 | 90000 | 0 | 81806 | 81806 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 122-21 One (1) Lot Wrap Reel (SLIVER) | [19 empty] | RDD-NFUS | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 23-Mar. 2, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-03-16 | 2021-03-16 |  | 2021-05-12 |  |  | GoP | 250000 | 250000 | 0 | 228480 | 228480 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 121-21 Two (2) Lots Vacuum Pump | [19 empty] | RDD-NFUS | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 23-Mar. 2, 2021 | N/A | N/A | N/A | N/A | N/A | Apr. 14, 2021 | Apr. 14, 2021 |  | 2021-05-12 |  |  | GoP | 200000 | 200000 | 0 | 165000 | 165000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 126-21 Various Office Supplies and General Merchandise Items | [19 empty] | RDD-CDABUS | NO | Shopping | N/A | Feb. 23-Mar. 2, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 199550 | 199550 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 125-21 One (1) Lot Installation of Silk Reeling Machine in Kalinga State University | [19 empty] | RDD-NFUS | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 23-Mar. 2, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 370000 | 370000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed Bid
| RFQ No. 124-21 One (1) Lot Installation of Throwing Machine to Negros Occidental | [19 empty] | RDD-NFUS | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 23-Mar. 2, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 620000 | 620000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed Bid
| RFQ No. 161-21 One (1) Unit Differential Pressure Tester | [19 empty] | TSD-Chem | NO | NP-53.9 - Small Value Procurement | N/A | Mar. 9-16, 2021 | N/A | N/A | N/A | N/A | N/A | June 18, 2021 | June 18, 2021 |  |  |  |  | GoP | 1000000 | 1000000 | 0 | 430800 | 430800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 156-21 (100 kgs) Pineapple Fiber (Unbrushed) | [19 empty] | RDD-NFUS | NO | NP-53.9 - Small Value Procurement | N/A | Mar. 9-16, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-03-26 | 2021-03-26 |  | 2021-05-11 |  |  | GoP | 71700 | 71700 | 0 | 68000 | 68000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 137-21 One (1) Lot Various Office Supplies and Devices | [19 empty] | TSD-MCPU | NO | Shopping | N/A | Mar. 9-16, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 147235.52 | 147235.52 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed Bid
| RFQ No. 155-21 One (1) Lot IT Peripherals and Consumables | [19 empty] | TSD-MCPU | NO | Shopping | N/A | Mar. 9-16, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 65964 | 65964 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed bid
| RFQ No. 170-21 One (1) Lot Precision Environmental Control System | [19 empty] | TSD-Chem | NO | NP-53.9 - Small Value Procurement | N/A | Mar. 10-17, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 1000000 | 1000000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed bid
| RFQ No. 172-21 Various Laboratory Supplies | [19 empty] | TSD-Chem | NO | Shopping | N/A | Mar. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 251000 | 251000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed bid
| RFQ No. 196-21 One (1) Lot MOnthly Subscription of 30 Mbps Internet Service (Burstable) 9/24 | [19 empty] | OD-PICTS | NO | Shopping | N/A | Mar. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A | Apr. 26, 2021 | Apr. 26, 2021 |  | 2021-05-18 |  |  | GoP | 99000 | 99000 | 0 | 99000 | 99000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 200-21 (3 Units) 3 Ton Air Conditioner | [19 empty] | TSD-MCPU | NO | Shopping | N/A | Mar. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A | Apr. 20, 2021 | Apr. 20, 2021 |  | 2021-05-14 |  |  | GoP | 600000 | 600000 | 0 | 510000 | 510000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 187-21 (100 kgs) Pineapple Fiber (unbrushed) | [19 empty] | RDD-NFUS | NO | Shopping | N/A | Mar. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 71700 | 71700 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 190-21 Rewinding of RYPIC's Degumming Machine Set-up Transformer with Installation and Service Fee | [19 empty] | TSD-MCPU | NO | Shopping | N/A | Mar. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A | Apr. 20, 2021 | Apr. 20, 2021 |  |  |  |  | GoP | 56000 | 56000 | 0 | 56000 | 56000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 195-21 Installation of Silk Reeling Machine (Misamis Oriental) | [19 empty] | RDD-NFUS | NO | NP-53.9 - Small Value Procurement | N/A | Mar. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 500000 | 500000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed bid
| RFQ No. 202-21 (R) 3 Units Desktop Computer | [19 empty] | TSD-Chem | NO | Shopping | N/A | Mar. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 240000 | 240000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed bid
| One (1) Unit Temperature amd Humidity Chamber | [19 empty] | TSD-Chem | NO | Competitive Bidding | N/A | Mar. 16-25,2021 | 2021-03-24 | Apr. 7, 2021 | Apr. 7, 2021 | Apr. 7, 2021 | June 9, 2021 | Jul. 8, 2021 | Jul. 8, 2021 | N/A | N/A | N/A | N/A | GoP | 1600000 | 0 | 1600000 | 1168888.88 | 0 | 1168888.88
| One (1) Unit Bacterial Filtration Efficiency Tester | [19 empty] | TSD-Chem | NO | Competitive Bidding | 2021-03-04 | Mar. 16-25,2021 | 2021-03-24 | Apr. 7, 2021 | Apr. 7, 2021 | Apr. 7, 2021 | June 9, 2021 | Jul. 8, 2021 | Jul. 8, 2021 | N/A | N/A | N/A | N/A | GoP | 9500000 | 0 | 9500000 | 4438888.88 | 0 | 4438888.88
| One (1) Unit Flex Tester | [19 empty] | TSD-Chem | NO | Competitive Bidding | N/A | Mar. 16-25,2021 | 2021-03-24 | Apr. 7, 2021 | Apr. 7, 2021 | Apr. 7, 2021 | June 9, 2021 | Jul. 8, 2021 | Jul. 8, 2021 | N/A | N/A | N/A | N/A | GoP | 2000000 | 0 | 2000000 | 1888888.88 | 0 | 1888888.88
| One (1) Unit Microbial Penetration Test System | [19 empty] | TSD-Chem | NO | Competitive Bidding | 2021-03-09 | Mar. 16-25,2021 | 2021-03-24 | Apr. 7, 2021 | Apr. 7, 2021 | Apr. 7, 2021 | June 9, 2021 | Jul. 13, 2021 | Jul. 13, 2021 | N/A | N/A | N/A | N/A | GoP | 3500000 | 0 | 3500000 | 2388000 | 0 | 2388000
| One (1) Lot Particle Filtration Efficiency Test System | [19 empty] | TSD-Chem | NO | Competitive Bidding | 2021-03-09 | Mar. 16-25,2021 | 2021-03-24 | Apr. 7, 2021 | Apr. 7, 2021 | Apr. 7, 2021 | June 10, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 14000000 | 0 | 14000000 | N/A | N/A | N/A
| RFQ No. 131-21 One (1) Unit Replacement of Steam Header attached to Steam Boiler | [19 empty] | RDD-NFUS | NO | Direct Contracting | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Mar. 9, 2021 | Mar. 9, 2021 |  | Apr. 15, 2021 |  |  | GoP | 300000 | 300000 | 0 | 298000 | 298000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 130-21 One (1) Lot Labor and Materials for the Installation of 3-phase Electrical Wiring System in Silk Processing Building | [19 empty] | RDD-NFUS | NO | Direct Contracting | N/A | Feb. 26-Mar. 5, 2021 | N/A | N/A | N/A | N/A | N/A | Mar. 9, 2021 | Mar. 9, 2021 |  | Apr. 26, 2021 |  |  | GoP | 465000 | 465000 | 0 | 443503.6 | 443503.6 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 132-21 240 kgs Water Repellent Finishing | [19 empty] | RDD-CDABUS | NO | NP-53.9 - Small Value Procurement | N/A | Mar. 3-8, 2021 | N/A | N/A | N/A | N/A | N/A | Apr. 19, 2021 | Apr. 19, 2021 |  | May 12, 2021 |  |  | GoP | 288000 | 288000 | 0 | 228000 | 228000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 222-21 Two (2) Kits DNA Extraction Kit 50 pres/kit | [19 empty] | RDD-NFUS | NO | Shopping | N/A | Mar. 24-31, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 58000 | 58000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed Bid
| RFQ No. 219-21 Bidirectional Capillary Sequencing / Sample Purification | [19 empty] | RDD-NFUS | NO | Shopping | N/A | Mar. 24-31, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 97000 | 97000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 203-21 One (1) Lot Laptop Computer | [19 empty] | RDD-NFUS | NO | Shopping | N/A | Mar. 24-31, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 80000 | 80000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed Bid
| RFQ No. 256-21 One (1) Unit Electric Motor Winding Machine | [19 empty] | TSD-MCPU | NO | Shopping | N/A | Mar. 30-Apr. 5, 2021 | N/A | N/A | N/A | N/A | N/A | Apr. 20, 2021 | Apr. 20, 2021 |  | May 24, 2021 |  |  | GoP | 600000 | 600000 | 0 | 595138 | 595138 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 232-21 One (1) Lot Video Conferencing Solution | [19 empty] | OD-PICTS | NO | Shopping | N/A | Mar. 25-Apr. 5, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 150000 | 150000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed Bid
| RFQ No. 228-21 AATCC Blue Wool Lightfastness Standards / Blue Wool Reference / Standard of Fading (5 & 20 AATCC Fading Unit) | [19 empty] | TSD-Physical | NO | NP-53.9 - Small Value Procurement | N/A | Mar. 25-Apr. 5, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 124000 | 124000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed Bid
| RFQ No. 245-21 200 kgs TEOS / 200 kgs OTES | [19 empty] | RDD - CDABUS | NO | Shopping | N/A | Mar. 25-Apr. 5, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 280000 | 280000 | 0 | 268000 | 268000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed Bid
| RFQ No. 261-21 One (1) pc Slatting Machine for Bamboo | [19 empty] | RDD-NFUS | NO | Shopping | N/A | Apr. 5-12, 2021 | N/A | N/A | N/A | N/A | 2021-05-07 | May 10, 2021 | May 10, 2021 |  |  |  |  | GoP | 500000 | 500000 | 0 | 420000 | 420000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 260-21 One (1) Lot 30Mbps Internet Service (Burstable) 9/24 | [19 empty] | RDD-CDABUS | NO | Shopping | N/A | Apr. 5-12, 2021 | N/A | N/A | N/A | N/A | N/A | Apr. 26, 2021 | Apr. 26, 2021 |  |  |  |  | GoP | 99000 | 99000 | 0 | 99000 | 99000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 259-21 One (1) Lot Hiring of Highly Technical Consultant for the Extablishment of the PTRI Microbiology Laboratory | [19 empty] | TSD-Chem | NO | NP-53.7 Highly Technical Consultants | N/A | Apr. 5-12, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 450000 | 450000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed Bid
| RFQ No. 258-21 One (1) Lot 30Mbps Internet Service (Bustable) 9/24 | [19 empty] | OD-PICTS | NO | Shopping | N/A | Apr. 5-12, 2021 | N/A | N/A | N/A | N/A | N/A | Apr. 22, 2021 | Apr. 22, 2021 |  |  |  |  | GoP | 99000 | 99000 | 0 | 99000 | 99000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 293-21 (R) One (1) Unit Synthetic Blood Penetration Tester | [19 empty] | RDD-NFUS | NO | Shopping | N/A | Apr. 7-12, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 1000000 | 1000000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed Bid
| RFQ No. 294-21 (R) 10 Units Laser / Laserjet Colored Printer | [19 empty] | OD-PICTS | NO | Shopping | N/A | Apr. 8-15, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 200000 | 200000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 295-21 Tetraethyl Orthosilicate, Purity 98% (TEOS) and Octyltriethoxysilane, Purity 98% (OTES) | [19 empty] | RDD-CDABUS | NO | Shopping | N/A | Apr. 8-15, 2021 | N/A | N/A | N/A | N/A | Jan. 25, 2021 | [6 empty] | GoP | 280000 | 280000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 317-21 One (1) Lot Test Weights | [19 empty] | TSD-Chem | NO | Shopping | N/A | Apr. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 55000 | 55000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed bid
| RFQ No. 324-21 One (1) Lot Various Laboratory Chemicals | [19 empty] | TSD-MCPU | NO | Shopping | N/A | Apr. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 149500 | 149500 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 322-21 Various Fibers (to be sourced out in the localities of Ilocos) | [19 empty] | TSD-MCPU | NO | Shopping | N/A | Apr. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 63500 | 63500 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 321-21 Various Fibers (to be sourced out in the localities of Ilo-ilo | [19 empty] | TSD-MCPU | NO | Shopping | N/A | Apr. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 63500 | 63500 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 046-21 60 Sets Tokens for Media and Speakers | [20 empty] | NO | Shopping | N/A |  | N/A | N/A | N/A | N/A | N/A | Feb. 1, 2021 | Feb. 1, 2021 |  |  |  |  | GoP | 90000 | 90000 | 0 | 81000 | 81000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 329-21 (R) One (1) Lot Security Cameras with Labor and Installation | [19 empty] | FAD-BTS | NO | Shopping | N/A | Apr. 15-22, 2021 | N/A | N/A | N/A | N/A | June 2, 2021 | June 4, 2021 | June 4, 2021 |  |  |  |  | GoP | 90000 | 90000 | 0 | 81806 | 81806 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 353-21 Two (2) Units Autoclave | [19 empty] | TSD-Chem | NO | NP-53.9 - Small Value Procurement | N/A | Apr. 22-29, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 800000 | 800000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 352-21 One (1) Lot Fiber Cutting Machine | [19 empty] | RDD-NFUS | NO | Shopping | N/A | Apr. 22-29, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 500000 | 500000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Potentiometric Analyzer | [19 empty] | RDD | NO | Competitive Bidding | N/A | Apr. 22-May 3, 2021 | Apr. 30, 2021 | 2021-05-12 | 2021-05-12 | N/A | June 23, 2021 | June 24, 2021 | June 25, 2021 |  |  |  |  | GoP | 1800000 | 0 | 1800000 | 1800000 | 0 | 1800000
| One (1) Unit Handheld Colorimeter | [19 empty] | RDD | NO | Competitive Bidding | N/A | Apr. 22-May 3, 2021 | Apr. 30, 2021 | 2021-05-12 | 2021-05-12 | N/A | N/A | June 24, 2021 | June 25, 2021 |  |  |  |  | GoP | 1200000 | 0 | 1200000 | 1188000 | 0 | 1188000
| RFQ No. 454-21 (R) Installation of Throwing Machine at Brgy. Tabunan, Bago City, Negros Occidental | [19 empty] | RDD-NFUS | NO | Shopping | N/A | May 5-10, 2021 | N/A | N/A | N/A | N/A | N/A | May 12, 2021 | May 12, 2021 |  |  |  |  | GoP | 620000 | 620000 | 0 | 615000 | 615000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 455-21 (R) Installation of Silk Reeling Machine at Kalinga State University | [19 empty] | RDD-NFUS | NO | Shopping | N/A | May 5-10, 2021 | N/A | N/A | N/A | N/A | N/A | May 12, 2021 | May 12, 2021 |  |  |  |  | GoP | 370000 | 370000 | 0 | 365300 | 365300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 456-21 (R) Installation of Silk Reeling Machine at Misamis Oriental | [19 empty] | RDD-NFUS | NO | Shopping | N/A | May 5-10, 2021 | N/A | N/A | N/A | N/A | N/A | May 12, 2021 | May 12, 2021 |  |  |  |  | GoP | 500000 | 500000 | 0 | 495000 | 495000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 453-21 (R) DNA Extraction Kit, for tissue and insects, bead-bashing format 50preps/kit | [19 empty] | RDD-NFUS | NO | Shopping | N/A | May 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 58000 | 58000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 441-21 90 samples Pilling Resistance (ASTM D3512) | [19 empty] | RDD-CDABUS | NO | Shopping | N/A | May 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | May 25, 2021 | May 25, 2021 |  |  |  |  | GoP | 85176 | 85176 | 0 | 85176 | 85176 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 2104-434 100 gallons, Alcohol 70% Solution | [19 empty] | TSD-Chem | NO | Shopping | N/A | May 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 75000 | 75000 | 0 | 30700 | 30700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 421-21 Three (3) Units Desktop Computer | [19 empty] | TSD-Chem | NO | Shopping | N/A | May 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | June 10, 2021 | June 10, 2021 |  |  |  |  | GoP | 240000 | 240000 | 0 | 154650 | 154650 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 414-21 (R) 15 Units Laptop | [19 empty] | OD-PICTS | NO | Shopping | N/A | May 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | May 27, 2021 | May 27, 2021 |  |  |  |  | GoP | 600000 | 600000 | 0 | 592500 | 592500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 381-21 2,000 pcs Paper Cones | [19 empty] | RDD-NFUS | NO | Shopping | N/A | May 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | May 20, 2021 | May 20, 2021 |  |  |  |  | GoP | 116000 | 116000 | 0 | 115000 | 115000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 450-21 (48 boxes) Nitirle Gloves, various sizes | [19 empty] | RDD-NFUS | NO | Shopping | N/A | May 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | May 18, 2021 | May 18, 2021 |  |  |  |  | GoP | 67200 | 67200 | 0 | 43200 | 43200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 458-21 (R) One (1) Lot Test Weights | [19 empty] | TSD-Chem | NO | Shopping | N/A | May 6-13, 2021 | N/A | N/A | N/A | N/A | N/A | May 18, 2021 | May 18, 2021 |  |  |  |  | GoP | 55000 | 55000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 457-21 (R) One (1) Lot Precision Environmental Control System | [19 empty] | TSD-Chem | NO | NP-53.9 - Small Value Procurement | N/A | May 6-13, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 1000000 | 1000000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed bid
| RFQ No. 460-21 (R) Various Toner Cart for HP | [19 empty] | TSD-Physical | NO | Shopping | N/A | May 7-14, 2021 | N/A | N/A | N/A | N/A | N/A | June 18, 2021 | June 18, 2021 |  |  |  |  | GoP | 62000 | 62000 | 0 | 38000 | 38000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 459-21 (R) One (1) Lot Consultancy Fees for the repair and renovation of the PTRI Testing Laboratories (Individual Consultant) | [19 empty] | TSD-Chem | NO | NP-53.7 Highly Technical Consultants | N/A | May 7-14, 2021 | N/A | N/A | N/A | N/A | June 4, 2021 | June 7, 2021 | June 7, 2021 |  |  |  |  | GoP | 290000 | 290000 | 0 | 234000 | 234000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 452-21 Four (4) Units Color Duplex Document Scanner | [19 empty] | OD-PICTS | NO | Shopping | N/A | May 12-19, 2021 | N/A | N/A | N/A | N/A | June 17, 2021 | Jul. 5, 2021 | Jul. 5, 2021 |  |  |  |  | GoP | 120000 | 120000 | 0 | 103800 | 103800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 502-21 One (1) Lot Videoconferencing Solution | [19 empty] | OD-PICTS | NO | Shopping | N/A | May 12-19, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 300000 | 300000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 533-21 One (1) Lot Glass Beads for Apparent Opening Size (1kg/pack) | [19 empty] | TSD-PHY | NO | Shopping | N/A | May 19-26, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 80000 | 80000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failed bid
| RFQ No. 535-21 (R) One (1) Lot Laptop Computer | [19 empty] | RDD-NFUS | NO | Shopping | N/A | May 19-26, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 80000 | 80000 | 0 | 79945 | 79945 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 409-21 One (1) Lot Preventive Maintenance for Perkin Elmer HPLC | [19 empty] | RDD-CDABUS | NO | Shopping | N/A | May 20-27, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 100000 | 100000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 506-21 150 meters Woven Fabric (100% Polyester) | [19 empty] | RDD-CDABUS | NO | Shopping | N/A | May 14-21, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 52500 | 52500 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 551-21 Three (3) Units Digital Copying Machine | [19 empty] | OD-PICTS | NO | Shopping | N/A | May 21-28, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 135000 | 135000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 567-21 One (1) Unit Laptop Computer | [19 empty] | RDD-NFUS | NO | Shopping | N/A | May 24-31, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 130000 | 130000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 568-21 One (1) Unit Vibrating Table | [19 empty] | RDD-NFUS | NO | Shopping | N/A | May 24-31, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 500000 | 500000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 575-21 One (1) Lot Installation of Receiving and Releasing Window | [19 empty] | FAD | NO | Shopping | N/A | May 27-June 3, 2021 | N/A | N/A | N/A | N/A | N/A | June 23, 2021 | June 23, 2021 |  |  |  |  | GoP | 150007.5 | 150007.5 | 0 | 120000 | 120000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 600-21 One (1) Lot Fiber Cutting Machine | [19 empty] | RDD-NFUS | NO | Shopping | N/A | June 4-11, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 300000 | 300000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 614-21 (R) One (1) Lot Precision Environmental Control System | [19 empty] | TSD-Chem | NO | NP-53.9 - Small Value Procurement | N/A | June 11-18, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 1000000 | 1000000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 637-21 One (1) Lot Stenter Machine | [19 empty] | RDD-CDABUS | NO | Shopping | N/A | June 14-21, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 600000 | 600000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 673-21 Two (2) Units Vibrating Trowel | [19 empty] | RDD-NFUS | NO | Shopping | N/A | June 18-25, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 200000 | 200000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 680-21 One (1) Lot Service Fee for the Delivery of Throwing Equipment from DOST-PTRI, Bicutan Taguig City to Brgy. Imelda, Villanueva, Misamis Oriental | [19 empty] | RDD-NFUS | NO | Shopping | N/A | June 18-25, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 195000 | 195000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 671-21 One (1) Unit Humidity Chamber | [19 empty] | RDD-NFUS | NO | Shopping | N/A | June 18-25, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 1000000 | 1000000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 669-21 One (1) Unit Laptop Computer | [19 empty] | RDD-NFUS | NO | Shopping | N/A | June 18-25, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 130000 | 130000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PR 2106-630 One (1) Lot Laboratory Preneedling Machine | [19 empty] | RDD | NO | Competitive Bidding | 2021-05-27 | June 18-July 7. 2021 | June 25, 2021 | Jul. 7, 2021 | Jul. 7, 2021 | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 3000000 | 0 | 3000000 | N/A | N/A | N/A
| PR 2106-666 One (1) Lot Spectrofluorometer | [19 empty] | RDD | NO | Competitive Bidding | 2021-05-27 | June 18-July 7. 2021 | June 25, 2021 | Jul. 7, 2021 | Jul. 7, 2021 | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 8000000 | 0 | 8000000 | N/A | N/A | N/A
| PR 2105-600 One (1) Unit Bursting Strength Tester | [19 empty] | TSD-Chem | NO | Competitive Bidding | N/A | June 18-July 7. 2021 | June 25, 2021 | Jul. 7, 2021 | Jul. 7, 2021 | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 1600000 | 0 | 1600000 | N/A | N/A | N/A
| PR 2106-622 One (1) Lot Distilling Apparatus | [19 empty] | RDD | NO | Competitive Bidding | N/A | June 18-July 7. 2021 | June 25, 2021 | Jul. 7, 2021 | Jul. 7, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 1200000 | 0 | 1200000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failure of bidding
| PR No. 2106-641 One (1) Lot Laboratory High Temperature Dyeing/ Degumming Machine | [19 empty] | RDD | NO | Competitive Bidding | 2021-05-27 | June 18-July 7. 2021 | June 25, 2021 | Jul. 14, 2021 | Jul. 14, 2021 | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 2200000 | 0 | 2200000 | N/A | N/A | N/A | [7 empty] | On going evaluation of end-user & TWG
| PR 2106-632 One (1) Lot Bamboo Extraction Machine | [19 empty] | RDD | NO | Competitive Bidding | N/A | June 18-July 7. 2021 | June 25, 2021 | Jul. 14, 2021 | Jul. 14, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 1200000 | 0 | 1200000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Failure of bidding
| RFQ No. 599-21 Two (2) Units Vibrating Trowel | [19 empty] | RDD | NO | Shopping | N/A | June 22-29, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 200000 | 200000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 702-21 (720) pieces N95 Respirator and Surgical Mask | [19 empty] | TSD-Chem | NO | Shopping | N/A | June 24-July 1, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | GoP | 144000 | 144000 | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 643-20 One (1) Lot Wrap Reel (Yarns) | [19 empty] | RDD | NO | Shopping | N/A | Jan. 13-20, 2021 | N/A | N/A | Jan. 20,2021 | N/A | N/A | Feb. 11, 2021 | Feb. 11, 2021 |  |  |  |  | GoP | 300000 | 300000 | 0 | 298000 | 298000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 430-21 100 gallons Alcohol, 70% solution for disinfection with FDA Philippines product notification | [19 empty] | TSD-Chem | NO | Shopping | N/A | May 3-10, 2021 | N/A | N/A | N/A | 2021-05-10 | N/A | May 17, 2021 | May 17,2021 | Jun. 18, 2021 | Jun. 21, 2021 | N/A | N/A | GoP | 75000 | 75000 | 0 | 30700 | 30700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 79323881.02
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | MARILOU G. AGUSTIN | [11 empty] | Dr. JULIUS L. LEAÑO, Jr. | [9 empty] | CELIA B. ELUMBA
[21 empty] | BAC Secretariat | [10 empty] | BAC Chairperson | [10 empty] | Director IV

## pmr (as of 12.31)
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | Philippine Textile Research Institute Procurement Monitoring Report as of December 31, 2021
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
Total Contract Price of Procurement Actitvites Conducted | [37 empty] | 0 |  |  | 0
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 0
0N-GOING PROCUREMENT ACTIVITIES
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 0
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | MARILOU G. AGUSTIN | [11 empty] | Dr. JULIUS L. LEAÑO, Jr. | [9 empty] | CELIA B. ELUMBA
[21 empty] | BAC Secretariat | [10 empty] | BAC Chairperson | [10 empty] | Director IV

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement