## PTRI 2nd Semester
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | Philippine Textile Research Institute Procurement Monitoring Report as of December 31, 2021
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| RFQ No. 062-21 Three (3) Packs Rubber Diaphragm | [19 empty] | TSD-Phy | NO | Direct Contracting | N/A | Feb. 2-9, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-05-21 | 2021-05-21 | GoP | 97500 | 97500 | 0 | 95000 | 95000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 063-21 One (1) Set Jaw Inserts, Vulkollan Smooth | [19 empty] | TSD-Phy | NO | Direct Contracting | N/A | Feb. 2-9, 2021 | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-03 | 2021-03-03 | 2021-03-03 | 2021-04-29 | 2021-04-29 | GoP | 180000 | 180000 | 0 | 176988.12 | 176988.12 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 078-21 Ten (10) Boxes, Multifiber Standard Adjacent Fabric ISO DW | [19 empty] | TSD-Chem | NO | Direct Contracting | N/A | Feb. 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-03-09 | 2021-03-09 | Apr. 26, 2021 | Apr. 26, 2021 | 2021-05-28 | 2021-05-28 | GoP | 57000 | 57000 | 0 | 54800 | 54800 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 081-21 One (1) Lot Multifiber Fabric FA #10 | [19 empty] | TSD-Chem | NO | Direct Contracting | N/A | Feb. 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | Feb. 19, 2021 | 2021-04-20 | Apr. 20, 2021 | 2021-04-29 | 2021-05-28 | 2021-05-28 | GoP | 200000 | 200000 | 0 | 174200 | 174200 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 082-21 Repair and Maintenance of Precision Air Conditioning System | [19 empty] | TSD-Chem | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 8-15, 2021 | N/A | N/A | N/A | N/A | 2021-03-15 | 2021-03-11 | 2021-03-11 | Apr. 26, 2021 | Apr. 26, 2021 | 2021-05-10 | 2021-05-10 | GoP | 230000 | 230000 | 0 | 200000 | 200000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 110-21 One (1) Lot Fabrication amd Installation of Customized Office Workstation | [19 empty] | OD-TIPS | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 22-Mar. 1, 2021 | N/A | N/A | N/A | N/A | 2021-03-15 | 2021-03-19 | 2021-03-19 | Apr. 29, 2021 | 2021-04-29 | 2021-05-14 | 2021-05-14 | GoP | 245000 | 245000 | 0 | 200000 | 200000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 002-21 (R) Toploading Balance / Digital Floor Scale | [19 empty] | RDD | NO | Shopping | N/A | January 18-25, 2021 | N/A | N/A | N/A | 2021-01-25 | N/A | 2021-04-08 | 2021-04-19 | 2021-04-29 | 2021-05-03 | 2021-06-02 | 2021-06-02 | GoP | 250000 | 250000 | 0 | 175000 | 175000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ no. 003-21 (R) One (1) Lot Moisture Analyzer | [19 empty] | RDD | NO | Shopping | N/A | January 15-21, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-04-06 | 2021-04-20 | 2021-05-03 | 2021-05-07 | 2021-07-10 | 2021-07-10 | GoP | 200000 | 200000 | 0 | 160000 | 160000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 013-21 Network Attached Storage (NAS) | [19 empty] | PICTS | NO | Shopping | N/A | Jan. 25-Feb 1, 2021 | N/A | N/A | N/A | 2021-02-01 | NA | 2021-03-26 | 2021-04-14 | 2021-04-23 | 2021-04-28 | 2021-06-28 | 2021-06-28 | GoP | 90000 | 90000 | 0 | 55440 | 55440 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 643-21 One (1) Lot Wrap Reel Yarns | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Jan 13 - 20, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-02-11 | 2021-03-08 | 2021-03-08 | 2021-03-11 | 2021-12-28 | 2021-12-28 | GoP | 300000 | 300000 | 0 | 298480 | 298480 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 061-21 One (1) Lot Replacement of Defective Condenser Fan Motor | [19 empty] | TSD | NO | Shopping | N/A | Feb. 2-09, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-04-28 | 2021-06-14 | 2021-06-14 | 2021-06-18 | 2021-07-22 | 2021-07-22 | GoP | 130000 | 130000 | 0 | 120000 | 120000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 086-21 One (1) Unit Impact Penetration Tester | [19 empty] | TSD | NO | Shopping | N/A | Feb. 8-15, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-02-19 | 2021-03-30 | 2021-03-30 | 2021-04-29 | 2021-05-28 | 2021-05-28 | GoP | 100000 | 100000 |  | 100000 | 100000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 091-21 Thirty five (35) units Application Software for Home and Business 2019 (Word, Excel, Powerpoint, Outlook) | [19 empty] | PICTS | NO | Shopping | N/A | Feb. 8-15, 2021 | NA | NA | NA | 2021-02-15 | NA | 2021-03-25 | 2021-03-29 | 2021-04-20 | 2021-04-29 | 2021-04-30 | 2021-04-30 | GoP | 700000 | 700000 | 0 | 343000 | 343000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 100-21 One (1) Lot Analytical Balance | [19 empty] | RDD | NO | Shopping | N/A | Feb. 11- 18, 2021 | NA | NA | NA | 2021-02-28 | NA | 2021-03-16 | 2021-04-14 | 2021-04-23 | 2021-04-28 | 2021-06-03 | 2021-06-03 | GoP | 197500 | 197500 | 0 | 145000 | 145000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 101-21 One (1) Unit Trinocular Microscope | [19 empty] | TSD | NO | Shopping | N/A | Feb.18-26, 2021 | [5 empty] | 2021-04-28 | 2021-04-30 | 2021-06-09 | 2021-06-15 | 2021-07-30 | 2021-07-30 | GoP | 100000 | 100000 | 0 | 90000 | 90000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 122-21 One (1) Lot Wrap Reel (SLIVER) | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 23-Mar. 2, 2021 | N/A | N/A | N/A | 2021-03-02 | N/A | 2021-03-16 | 2021-03-29 | 2021-05-12 | 2021-05-17 | 2021-12-10 | 2021-12-10 | GoP | 250000 | 250000 | 0 | 228480 | 228480 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 121-21 Two (2) Lots Vacuum Pump | [19 empty] | RDD | NO | Shopping | N/A | Feb. 23-Mar. 2, 2021 | N/A | N/A | N/A | 2021-03-02 | N/A | 2021-04-27 | 2021-05-12 | 2021-05-12 | 2021-05-17 | 2021-07-13 | 2021-07-13 | GoP | 200000 | 200000 | 0 | 165000 | 165000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 132-21 240kgs Water Repellent Finishing | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Mar. 3-8, 2021 | N/A | N/A | N/A | 2021-03-08 | N/A | 2021-04-19 | 2021-04-27 | 2021-05-12 | 2021-05-14 | 2021-05-17 | 2021-05-17 | GoP | 288000 | 288000 | 0 | 228000 | 228000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 161-21 One (1) Unit Differential Pressure Tester | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Mar. 9-16, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-06-18 | 2021-07-12 | 2021-07-12 | 2021-08-04 | 2021-10-08 | 2021-10-08 | GoP | 1000000 | 1000000 | 0 | 430800 | 430800 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 190-21 Rewinding of RYPIC's Degumming Machine Step-up Transformer with Installation and Service Fee | [19 empty] | TSD | NO | Shopping | N/A | Mar. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-04-20 | 2021-06-09 | 2021-06-09 | 2021-06-14 | 2021-06-09 | 2021-06-09 | GoP | 56000 | 56000 | 0 | 56000 | 56000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 200-21 (3 Units) 3 Ton Air Conditioner | [19 empty] | TSD | NO | Shopping | N/A | Mar. 15-22, 2021 | N/A | N/A | N/A | 2021-03-22 | N/A | 2021-04-20 | 2021-04-27 | 2021-05-14 | 2021-05-19 | 2021-05-26 | 2021-05-26 | GoP | 600000 | 600000 | 0 | 510000 | 510000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Unit Bacterial Filtration Efficiency Tester | [19 empty] | TSD | NO | Competitive Bidding | Mar.4, 2021 | Mar. 16-25, 2021 | 2021-03-04 | 2021-04-05 | Apr.7, 2021 | Apr.7, 2021 | 2021-06-09 | 2021-07-08 | 2021-08-05 | 2021-08-05 | 2021-09-01 | 2021-11-15 | 2021-11-15 | GoP | 9500000 | 0 | 9500000 | 4438888.88 | 0 | 4438888.88 | COA/PCCI | 2021-03-16 | 2021-03-16 | 2021-03-16 | 2021-03-16 | N/A | N/A
| RFQ No. 256-21 One (1) Unit Electric Motor WInding Machine | [19 empty] | TSD | NO | Shopping | N/A | Mar. 30- Apr. 5, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-04-20 | 2021-05-20 | 2021-05-20 | 2021-05-24 | 2021-09-22 | 2021-09-22 | GoP | 600000 | 600000 | 0 | 595138 | 595138 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ NO. 157-21 100 kgs Pineapple FIber (decorticated) | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Mar. 31-Apr.5, 2021 | N/A | N/A | N/A | 2021-04-05 | N/A | 2021-04-14 | 2021-04-26 | 2021-05-11 | 2021-05-18 | 2021-07-30 | 2021-07-30 | GoP | 88800 | 88800 | 0 | 85000 | 85000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 261-21 One (1) pc. Slatting Machine for Bamboo | [19 empty] | RDD | NO | Shopping | N/A | Apr. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-05-10 | 2021-06-15 | 2021-06-15 | 2021-06-21 | 2021-09-03 | 2021-09-03 | GoP | 500000 | 500000 | 0 | 420000 | 420000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 329-21 (R) One (1) Lot Security Cameras with Labor and Installation | [19 empty] | FAD | NO | Shopping | N/A | Apr. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-06-04 | 2021-07-14 | 2021-07-14 | 2021-07-26 | 2021-08-03 | 2021-08-03 | GoP | 90000 | 90000 | 0 | 81806 | 81806 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 353-21 Two (2) Units Autoclave | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Apr. 22-May 3, 2021 | NA | NA | NA | 2021-05-03 | NA | 2021-08-04 | 2021-08-13 | 2021-09-09 | 2021-09-14 | 2021-11-11 | 2021-11-11 | GoP | 800000 | 800000 | 0 | 580000 | 580000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Potentiometric Analyzer | [19 empty] | RDD | NO | Competitive Bidding | N/A | Apr. 22-May 3, 2021 | 2021-04-30 | 2021-05-12 | 2021-05-12 | 2021-05-12 | 2021-06-23 | 2021-06-24 | 2021-08-05 | 2021-08-05 | 2021-08-31 | 2021-11-09 | 2021-11-09 | GoP | 1800000 | 0 | 1800000 | 1800000 | 0 | 1800000 | COA/PCCI | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 | N/A | N/A
| RFQ No. 414-21 (R) 15 Units Laptop | [19 empty] | PICTS | NO | Shopping | N/A | May 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-05-27 | 2021-07-07 | 2021-07-07 | 2021-07-16 | 2021-07-19 | 2021-07-19 | GoP | 600000 | 600000 | 0 | 592500 | 592500 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 441-21 90 Samples Pilling Resistance (ASTM D3512) | [19 empty] | RDD | NO | Shopping | N/A | May 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-05-25 | 2021-07-05 | 2021-07-05 | 2021-07-12 | 2021-07-14 | 2021-07-14 | GoP | 85176 | 85176 | 0 | 85176 | 85176 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 454-21 (R) Installation of Throwing Machine at Brgy. Tanunan, Bago City, Negros Occidental | [19 empty] | RDD | NO | Shopping | N/A | May 5-10, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-05-12 | 2021-10-25 | 2021-10-25 | 2021-10-29 | 2021-11-16 | 2021-11-16 | GoP | 620000 | 620000 | 0 | 615000 | 615000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 455-21 (R) Installation of Silk Reeling Machine at Kalinga State University | [19 empty] | RDD | NO | Shopping | N/A | May 5-10, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-05-21 | 2021-07-06 | 2021-07-06 | 2021-07-09 | 2021-07-28 | 2021-07-28 | GoP | 370000 | 370000 | 0 | 365300 | 365300 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 458-21 (R) One (1) Lot Test Weights | [19 empty] | TSD | NO | Shopping | N/A | May 6-13, 2021 | NA | NA | NA | 2021-05-13 | NA | 2021-08-18 | 2021-08-25 | 2021-09-07 | 2021-09-10 | 2021-10-19 | 2021-10-19 | GoP | 55000 | 55000 | 0 | 54994.8 | 54994.8 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 459-21 (R) One (1) Lot Consultancy Fees for the Repair and Renovation of the PTRI Testing Laboratories (Individual Consultant) | [19 empty] | TSD | NO | NP-53.7 Highly Technical Consultants | N/A | May 7-14, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-06-07 | 2001-07-07 | 2021-07-07 | 2021-07-16 | 2021-10-27 | 2021-10-27 | GoP | 290000 | 290000 | 0 | 234000 | 234000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 452-21 Four (4) Units Color Duplex Document Scanner | [19 empty] | PICTS | NO | Shopping | N/A | May 12-19,2021 | N/A | N/A | N/A | N/A | N/A | 2021-07-05 | 2021-07-19 | 2021-07-19 | 2021-08-31 | 2021-10-13 | 2021-10-13 | GoP | 120000 | 120000 | 0 | 103800 | 103800 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| Installation of Three-Phase Electrical Wiring System at SPB and Loomweaving Building | [19 empty] | RDD | NO | Direct Contracting | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-14 | 2021-05-14 | 2021-05-14 | 2021-05-14 | 2021-06-28 | 2021-06-28 | GoP | 465000 | 465000 | 0 | 443503.6 | 443503.6 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| Replacement of Steam Header, CIMECH CSII SH8D | [19 empty] | RDD | NO | Direct Contracting | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-09 | 2021-04-15 | 2021-04-15 | 2021-04-30 | 2021-10-21 | 2021-10-21 | GoP | 300000 | 300000 | 0 | 298000 | 298000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 535-21 (R) One (1) Lot Laptop Computer | [19 empty] | RDD | NO | Shopping | N/A | May 19-26, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-07-08 | 2021-07-29 | 2021-07-29 | 2021-08-02 | 2021-08-03 | 2021-08-03 | GoP | 80000 | 80000 | 0 | 79945 | 79945 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 637-21 One (1) Lot Stenter Machine | [19 empty] | RDD | NO | Shopping | N/A | June 14-21, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-07-23 | 2021-08-04 | 2021-08-04 | 2021-08-09 | 2021-10-04 | 2021-10-04 | GoP | 600000 | 600000 | 0 | 595137 | 595137 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 725-21 AATCC Blue Wool Lightfastness Standards | [19 empty] | TSD | NO | Shopping | N/A | July 7 - 14, 2021 | NA | NA | NA | 2021-07-14 | NA | 2021-08-02 | 2021-08-17 | 2021-09-07 | 2021-09-14 | 2021-10-22 | 2021-10-22 | GoP | 124000 | 124000 | 0 | 122797 | 122797 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 757-21 (R) One (1) Lot Glass Bead for Apparent Opening Size (1kg/pack) | [19 empty] | TSD | NO | Shopping | N/A | July 15-22, 2021 | NA | NA | NA | 2021-07-22 | NA | 2021-08-02 | 2021-08-09 | 2021-09-07 | 2021-09-10 | 2021-09-20 | 2021-09-20 | GoP | 80000 | 80000 | 0 | 79000 | 79000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 815-21 Three (3) Units Digital Copying Machine | [19 empty] | PICTS | NO | Shopping | N/A | July 27- August 3, 2021 | NA | NA | NA | 2021-08-03 | NA | 2021-09-20 | 2021-09-20 | 2021-10-13 | 2021-10-18 | 2021-10-23 | 2021-10-23 | GoP | 180000 | 180000 | 0 | 170640 | 170640 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Unit Thermal Conductivity Analyzer | [19 empty] | RDD | NO | Competitive Bidding | 2021-07-02 | July 27- August 2, 2021 | 2021-08-04 | Aug. 24, 2021 | Aug. 24, 2021 | Aug. 24, 2021 | NA | 2021-09-13 | 2021-10-07 | 2021-10-22 | 2021-10-25 | 2021-12-10 | 2021-12-10 | GoP | 6000000 | 0 | 6000000 | 5860000 | 0 | 5860000 | COA/PCCI | 2022-07-27 | 2022-07-27 | 2022-07-27 | 2022-07-27 | N/A | N/A
| RFQ No. 861-21 One (1) Lot Digitizer | [19 empty] | RDD | NO | Shopping | N/A | Aug. 16-23, 2021 | NA | NA | NA | 2021-08-23 | NA | 2021-08-27 | 2021-09-07 | 2021-09-20 | 2021-09-23 | 2021-11-22 | 2021-11-22 | GoP | 260000 | 260000 | 0 | 260000 | 260000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 915-21 (R) One (1) Lot Fiber Cutting Machine | [19 empty] | RDD | NO | Shopping | N/A | Aug. 18-25, 2021 | NA | NA | NA | 2021-08-25 | NA | 2021-09-27 | 2021-09-27 | 2021-10-15 | 2021-10-28 | 2021-12-16 | 2021-12-16 | GoP | 300000 | 300000 | 0 | 288250 | 288250 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 995-21 (R) Two (2) Units Vibrating Trowel | [19 empty] | RDD | NO | Shopping | N/A | Sept. 1-3, 2021 | NA | NA | NA | 2021-09-03 | NA | 2021-09-15 | 2021-09-21 | 2021-10-21 | 2021-10-21 | 2021-11-29 | 2021-11-29 | GoP | 200000 | 200000 | 0 | 194000 | 194000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 916-21A (R) One (1) Lot Repair and Renovation of Long Staple Fiber Pilot Plant Extension | [19 empty] | RDD | NO | Shopping | N/A | Sept. 13-20, 2021 | N/A | N/A | N/A | 2021-09-20 | N/A | 2021-09-21 | 2021-09-28 | 2021-10-11 | 2021-10-14 | 2021-12-21 | 2021-12-21 | GoP | 968929.56 | 968929.56 | 0 | 901963.86 | 901963.86 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 975-21 One Hundred (100) licenses Antivirus and Anti-Malware | [19 empty] | PICTS | NO | Shopping | N/A | Sept. 20-27, 2021 | NA | NA | NA | 2021-09-27 | NA | 2021-10-06 | 2021-10-14 | 2021-10-26 | 2021-10-28 | 2021-11-10 | 2021-11-10 | GoP | 250000 | 250000 | 0 | 156000 | 156000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1076-21 One (1) Lot Degumming System Repair | [19 empty] | RDD | NO | Shopping | N/A | Sept. 23-29, 2021 | N/A | N/A | N/A | 2021-09-29 | N/A | 2021-09-30 | 2021-10-05 | 2021-10-13 | 2021-10-22 | 2021-10-27 | 2021-10-27 | GoP | 110000 | 110000 | 0 | 110000 | 110000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1098-21 One (1) Lot Repair and Renovation of Long Staple Fiber Pilot Plant Extension Ph. II | [19 empty] | RDD | NO | Shopping | N/A | Sept. 30 - Oct. 7, 2021 | NA | NA | NA | 2021-10-07 | NA | 2021-10-14 | 2021-10-14 | 2021-10-25 | 2021-11-05 | 2021-12-20 | 2021-12-20 | GoP | 399730.8 | 399730.8 | 0 | 364259.28 | 364259.28 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Respirator Resistance Tester | [19 empty] | TSD | NO | Competitive Bidding | 2021-11-16 | Nov. 18-24, 2021 | 2021-11-25 | Dec. 9, 2021 | Dec. 9, 2021 | Dec. 9, 2021 | NA | 2021-01-21 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-12-03 | 2021-12-03 | GoP | 2700000 | 0 | 2700000 | 1298000 |  | 1298000 | COA/PCCI | 2021-11-18 | 2021-11-18 | 2021-11-18 | 2021-11-18 | N/A | N/A
| RFQ No. 007-21 (R) 3 Units Handheld Label Maker | [19 empty] | TSD | NO | Shopping | N/A | Jan.18-25, 2021 | N/A | N/A | N/A | 2021-01-25 | N/A | 2021-03-25 | 2021-04-20 | 2021-05-04 | 2021-05-07 | 2021-05-21 | 2021-05-21 | GoP | 54000 | 54000 | 0 | 42109 | 42109 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 046-21 Tokens for Media and speakers | [19 empty] | OD | NO | NP-53.9 - Small Value Procurement | N/A | Jan.28-Feb.1, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-02-01 | 2021-01-28 | 2021-01-28 | 2021-01-28 | 2021-01-28 | 2021-01-28 | GoP | 90000 | 90000 | 0 | 81000 | 81000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ no. 065-21 THree (3) Units 24-port Gigabit Managed Switch | [19 empty] | PICTS | NO | Shopping | N/A | Feb. 02-09, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-03-05 | 2021-03-19 | 2021-03-19 | 2021-04-16 | 2021-04-19 | 2021-04-19 | GoP | 69000 | 69000 | 0 | 58125 | 58125 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 079-21 Forty (40) pcs Glass Gooch Crucible, Low Form | [19 empty] | TSD | NO | Shopping | N/A | Feb. 3-10, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-02-19 | 2021-03-18 | 2021-03-18 |  | 2021-03-24 | 2021-03-24 | GoP | 54000 | 54000 | 0 | 53000 | 53000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 110-21 One (1) Lot Fabrication and Installation of Customized Office Workstation | [19 empty] | TIPS | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 22- Mar. 1, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-03-19 | 2021-04-08 | 2021-04-08 | 2021-05-10 | 2021-05-14 | 2021-05-14 | GoP | 245000 | 245000 | 0 | 200000 | 200000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 187-21 (100kgs) Pineapple Fiber (unbrushed) | [19 empty] | RDD | NO | Shopping | N/A | Mar.15-22, 2021 | N/A | N/A | N/A | 2021-03-22 | NA | 2021-05-31 | 2021-04-19 | 2021-05-11 | 2021-05-14 | 2021-07-30 | 2021-07-30 | GoP | 71700 | 71700 | 0 | 68000 | 68000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 352-21 One (1) Lot Fiber Cutting Machine | [19 empty] | RDD | NO | Shopping | N/A | Apr. 22-29, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-07-23 | 2021-07-27 | 2021-08-16 | 2021-09-01 | 2021-10-19 | 2021-10-19 | GoP | 500000 | 500000 | 0 | 495000 | 495000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 456-21 (R) Installation of Silk Reeling Machine at Misamis Oriental | [19 empty] | RDD | NO | Shopping | N/A | May 5-10, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-05-21 | 2021-11-19 | 2021-11-19 | 2021-12-04 | 2021-12-07 | 2021-12-07 | GoP | 500000 | 500000 | 0 | 495000 | 495000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ NO. 409-21 One (1) Lot Preventive Maintenance for Perkin Elmer HPLC | [19 empty] | RDD | NO | Shopping | N/A | May 20-27, 2021 | N/A | N/A | N/A | N/A | N/A |  | 2021-07-05 | 2021-07-05 |  | 2021-07-30 | 2021-07-30 | GoP | 100000 | 100000 | 0 | 100000 | 100000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 575-21 One (1) Lot Installation of Receiving and Releasing Windows | [19 empty] | FAD | NO | Shopping | N/A | May 27- June 3, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-06-23 | 2021-08-03 | 2021-08-03 | 2021-08-06 | 2021-08-12 | 2021-08-12 | GoP | 150007.5 | 150007.5 | 0 | 120000 | 120000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ no. 702-21 (720) pcs N95 Respirator and Surgical Mask | [19 empty] | TSD | NO | Shopping | NA | June 24-July 1, 2021 | NA | NA | NA | 2021-07-01 | NA | 2021-08-26 | 2021-09-13 | 2021-09-22 | 2021-10-11 | 2021-10-12 | 2021-10-12 | GoP | 144000 | 144000 | 0 | 118800 | 118800 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 802-21 (R) One (1) Unit Synthetic Blood Penetration Tester | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | NA | July 23-26, 2021 | NA | NA | NA | 2021-07-26 | NA | 2021-08-02 | 2021-08-10 | 2021-09-09 | 2021-09-18 | 2021-12-02 | 2021-12-02 | GoP | 1000000 | 1000000 | 0 | 488000 | 488000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 895-21 One (1) Lot Service Fee for the delivery of Throwing Equipment from DOST, PTRI, Bicutan Taguig City to Brgy. Imelda Villanueva, Misamis Oriental | [19 empty] | RDD | NO | Shopping | N/A | Aug. 18-25, 2021 | N/A | N/A | N/A | 2021-08-25 | N/A | 2021-09-24 | 2021-09-27 | 2021-10-14 | 2021-10-19 | 2021-10-28 | 2021-10-28 | GoP | 195000 | 195000 | 0 | 195000 | 195000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 998-21 (R) Non-medical Face Mask Testing, ASTM (one Sample) | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | NA | Sept. 1-6, 2021 | NA | NA | NA | 2021-09-06 | NA | 2021-10-06 | 2021-10-14 | 2021-11-04 | 2021-11-08 | 2021-11-24 | 2021-11-24 | GoP | 150000 | 150000 | 0 | 113344 | 113344 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1000-21 (R) One (1) Lot Medical Face Mask Testing (one sample) | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | NA | Sept. 1-6, 2021 | NA | NA | NA | 2021-09-06 | NA | 2021-10-06 | 2021-10-14 | 2021-10-30 | 2021-11-02 | 2021-12-06 | 2021-12-06 | GoP | 300000 | 300000 | 0 | 265950.72 | 265950.72 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 962-21 Three (3) Units Desktop Computer | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | NA | Sept. 1-8, 2021 | NA | NA | NA | 2021-09-08 | NA | 2021-10-12 | 2021-11-09 | 2021-11-15 | 2021-11-18 | 2021-12-02 | 2021-12-02 | GoP | 249000 | 249000 | 0 | 219300 | 219300 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 963-21 One (1) Lot Replacement of Defective Lamp (Hitachi U-2900 UV VIS) | [19 empty] | RDD | NO | Direct Contracting | NA | NA | NA | NA | NA | NA | NA | 11-12-2021 | 11-12-2021 | 11-12-2021 | 11-12-2021 | 2021-12-06 | 2021-12-06 | GoP | 55000 | 55000 | 0 | 52000 | 52000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1068-21 Two (2) Units Visual Display Unit (Monitor) | [19 empty] | PICTS | NO | Shopping | NA | Sept. 23-30, 2021 | NA | NA | NA | 2021-09-30 | NA | 2021-10-08 | 2021-10-14 | 2021-10-28 | 2021-11-02 | 2021-12-06 | 2021-12-06 | GoP | 10000 | 10000 | 0 | 95000 | 95000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 964-21 2 Units ATP Meter | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | NA | Oct. 6-11, 2021 | NA | NA | NA | 2021-10-11 | NA | 2021-10-25 | 2021-11-04 | 2021-11-11 | 2021-11-15 | 2021-12-01 | 2021-12-01 | GoP | 300000 | 300000 | 0 | 281500 | 281500 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1166-21 (R) One (1) Lot Desktop Computer with accessories and software | [19 empty] | RDD | NO | Shopping | NA | Oct. 14-18, 2021 | NA | NA | NA | 2021-10-18 | NA | 2021-10-26 | 2021-10-28 | 2021-11-05 | 2021-11-12 | 2021-11-12 | 2021-11-12 | GoP | 120000 | 120000 | 0 | 119500 | 119500 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1151-21 ONe (1) Lot Design, Development and HOsting of Virtual Exhibition including PTRI Testing Services for the NSTW from Nov. 22-28, 2021 | [19 empty] | TIPS | NO | Shopping | NA | Oct. 13-15, 2021 | NA | NA | NA | 2021-10-15 | NA | 2021-10-19 | 2021-10-20 | 2021-10-22 | 2021-11-22 | 2021-11-29 | 2021-11-29 | GoP | 400000 | 400000 | 0 | 392000 | 392000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Laboratory Yarn Singeing Machine | [19 empty] | RDD | NO | Competitive Bidding | 2021-08-04 | 2021-08-11 | 2021-08-18 | 2021-08-31 | 2021-08-31 | 2021-08-31 | NA | NA | NA | NA | NA | NA | NA | GoP | 0 | 0 | 0 | 0 | 0 | 0 | COA/PCCI | 2021-08-11 | 2021-08-11 | 2021-08-11 | 2021-08-11 | N/A | N/A | FAILED BID.
| RFQ No. 1210-21 One (1) Unit Desktop Computer with Accessories and software | [19 empty] | RDD | NO | Shopping | NA | Oct. 27- Nov. 2, 2021 | NA | NA | NA | 2021-11-02 | NA | 2021-11-04 | 2021-11-04 | 2021-11-04 | 2021-11-04 | 2021-12-01 | 2021-12-01 | GoP | 120000 | 120000 | 0 | 119894.5 | 119894.5 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1276-21 One (1) Lot Custom Design and Development Add-ons of Virtual Exhibition for the NSTW from Nov.22-28, 2021 | [19 empty] | TIPS | NO | NP-53.9 - Small Value Procurement | NA | Nov.15-18,2021 | NA | NA | NA | 2021-11-18 | NA | 2021-11-18 | 2021-11-18 | 2021-11-22 | 2021-11-22 | 2021-11-28 | 2021-11-29 | GoP | 180000 | 180000 | 0 | 175840 | 175840 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A
[38 empty] | 0 |  |  | 0
Total Alloted Budget of Procurement Activities | [37 empty] | 39064343.86
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 29627650.76
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 9436693.1
0N-GOING PROCUREMENT ACTIVITIES
| RFQ No. 064-21 One (1) Lot 30Mbps Internet Services | [19 empty] | PICTS | NO | Shopping | N/A | Feb. 02-09, 2021 | N/A | N/A | N/A | N/A | N/A | [6 empty] | GoP | 264000 | 264000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 071-21 Five-hundred (500) kgs Cotton Fibers | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 3-10, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 65000 | 65000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 099-21 One (1) Lot Various Fabrics | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 11-18, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 72000 | 72000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 102-21 Two (2) Units Autoclave | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Feb. 18-26, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 800000 | 800000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 106-21 One (1) Unit Photoshop CC License / One (1) Unit Indesign CC License | [19 empty] | TIPS | NO | Shopping | N/A | Feb. 18-26, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 60000 | 60000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 219-21 Bidirectional Capillary Sequencing / sample Purification | [19 empty] | RDD | NO | Shopping | N/A | Mar. 24 - 31, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 97000 | 97000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 258-21 One (1) Lot 30Mbps Internet Service (Burstable) 9/24 | [19 empty] | RDD | NO | Shopping | N/A | Apr. 5-12, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 99000 | 99000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 294-21 (R) 10 Units Laser/Laserjet Colored Printer | [19 empty] | PICTS | NO | Shopping | N/A | Apr. 8-15, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 200000 | 200000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 295-21 TEOS 98% and OTES 98% Purity | [19 empty] | RDD | NO | Shopping | N/A | Apr. 8-15, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 280000 | 280000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 453-21 (R) DNA Extraction Kit, for tissue and insects, bead bashing format, 50preps/kit | [19 empty] | RDD | NO | Shopping | N/A | May 3-10, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 58000 | 58000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 421-21 Three (3) Units Desktop Computer | [19 empty] | TSD | NO | Shopping | N/A | May 3-10, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 240000 | 240000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 567-21 One (1) Unit Laptop Computer | [19 empty] | RDD | NO | Shopping | N/A | May 24-31, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 130000 | 130000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 568-21 One (1) Unit Vibrating Table | [19 empty] | RDD | NO | Shopping | N/A | May 24-31, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 500000 | 500000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 600-21 One (1) Lot Fiber Cutting Machine | [19 empty] | RDD | NO | Shopping | N/A | June 4-25,2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 300000 | 300000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ no. 599-21 Two (2) Units Vibrating Trowel | [19 empty] | RDD | NO | Shopping | N/A | Jun 22-29, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 200000 | 200000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 791-21 150 kgs Raw Bandala Fiber (extracted and dried, packaged in bags or bales) | [19 empty] | RDD | NO | Shopping | N/A | July 23-30, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 75000 | 75000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 857-21 (R) 3 Units Desktop Computer | [19 empty] | TSD | NO | Shopping | N/A | Aug. 3-10, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 240000 | 240000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 917-21 One (1) Lot Laptops and Tablets | [19 empty] | RDD | NO | Shopping | N/A | Aug. 19-26, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 505490 | 505490 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 993-21 (R) 3 Units Mechanical Fiber Extraction Machine | [19 empty] | RDD | NO | Shopping | N/A | Sept. 1-3, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 300000 | 300000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 996-21 (R) One (1) Lot Medical Face Mask Testing for Standard ASTM F2100 | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Sept. 1-3, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 220000 | 220000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 997-21 (R) 15kgs HeiQ Virblock NPJ03 | [19 empty] | RDD | NO | Shopping | N/A | Sep.1-3, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 150000 | 150000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 999-21 (R) Non-medical Face mask testing, ASTM (one sample) | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Sept. 1-6, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 10000 | 10000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 942-21 (25kgs) Healthguard AMIC | [19 empty] | RDD | NO | Shopping | N/A | Sept. 1-8, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 70000 | 70000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 952-21 One (1) Lot AATCC Testing Materials and Consumables | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Sept. 1-8, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 350000 | 350000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 967-21 One (1) Lot Extractor Arm Fume Hood Setup | [19 empty] | TSD | NO | Shopping | N/A | Sept. 1-8, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 35000 | 35000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 979-21 Ten (10) Units Laserjet Colored Printer | [19 empty] | PICTS | NO | Shopping | N/A | Sept. 13-20, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 200000 | 200000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1013-21 Eighteen (18) Samples Testing Services | [19 empty] | RDD | NO | Shopping | N/A | Sept. 20-24, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 105300 | 105300 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1037-21 One (1) Unit Laptop Computer with Accessories and Software | [19 empty] | RDD | NO | Shopping | N/A | Sept. 20-24, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 13000 | 13000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Conceptualization, editorial, writing, lay-out and design of PTRI Annual Report 2020 | [19 empty] | PICTS | NO | Shopping | N/A | Sept. 23-30, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 110000 | 110000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1055-21 One (1) Unit Fiber Melting Point Meter | [19 empty] | TSD | NO | Shopping | N/A | Sept. 28-Oct.1, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 150000 | 150000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1087-21 Three (3) Units Mechanical Fiber Extraction Machine | [19 empty] | RDD | NO | Shopping | N/A | Sept. 28-Oct.1, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 300000 | 300000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1090-21 (R) 3 Drums TEOS and 3 Drums OTES | [19 empty] | RDD | NO | Shopping | N/A | Sept. 28-Oct.1, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 60000 | 60000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1112-21 (R) Six (6) Samples Testing Services | [19 empty] | RDD | NO | Shopping | N/A | Oct. 6-11, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 54000 | 54000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1064-21 110 yards Professional Weaving (handloom) services | [19 empty] | RDD | NO | Shopping | N/A | Oct. 6-11, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 55000 | 55000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1084-21 Eighteen (18) samples Testing Services | [19 empty] | RDD | NO | Shopping | N/A | Oct. 6-11, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 117936 | 117936 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1107-21 100kgs Pineapple Leaf Fibers (unbrushed and decorticated) | [19 empty] | RDD | NO | Shopping | N/A | Oct. 6-11, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 70000 | 70000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Laboratory Yarn Singeing Machine | [19 empty] | RDD | NO | Competitive Bidding | N/A | Sept. 21, 2021 | Sept. 28, 2021 | N/A | 2021-10-12 | 2021-10-12 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 0 | 0 | 0 |  |  |  | COA/PCCI | Sept. 21, 2021 | Sept. 21, 2021 | Sept. 21, 2021 | Sept. 21, 2021 | N/A | N/A | FAILED BID.
| One (1) Lot Laboratory Yarn Singeing Machine | [19 empty] | RDD | NO | NP-53.1 Two Failed Biddings | N/A | 2021-10-19 | 2021-10-26 | N/A | 2021-11-05 | 2021-11-05 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 0 | 0 | 0 |  |  |  | COA/PCCI | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-10-20 | N/A | N/A | FAILED BID.
| One (1) Lot Laboratory Yarn Singeing Machine | [19 empty] | RDD | NO | Direct Contracting | N/A | Oct. 20 - Nov. 5, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 3900000 | 0 | 3900000 |  |  |  | COA/PCCI | N/A | N/A | N/A | N/A | N/A | N/A | Thru Letter of Credit
| RFQ No. 1025-21 One (1) Lot Latest Version of ASTM Standard Test Methods | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Oct. 20-25, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 80000 | 80000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1148-21 One (1) Lot Extractor Arm Fume Hood Set Up | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Oct. 20-26, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 350000 | 350000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1149-21 One (1) Lot Temperature Regulation System | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Oct. 20-26, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 800000 | 800000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1207-21 One (1) Lot Repair of Taber Abrasion Tester | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Oct. 20-27, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 145500 | 145500 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1203-21 One (1) Lot Renovation of the PTRI Testing Laboratory (Face Mask Testing) | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Oct. 20-25, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 759885.78 | 759885.78 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Supply of Labor, Materials, Tools, Equipment and Technical Supervision for the Detailed Architectural and Engineering Design (DAED) and Construction... | [19 empty] | RDD | YES | Competitive Bidding | 2021-10-20 | Oct. 26-Nov. 2, 2021 | Nov.2, 2021 | Nov.16,2021 | Nov.16,2021 | Nov.16,2021 | 2021-12-10 |  | N/A | N/A | N/A | N/A | N/A | GoP | 20000000 | 0 | 20000000 |  |  |  | COA/PCCI | 2021-10-26 | 2021-10-26 | 2021-10-26 | 2021-10-26 | N/A | N/A | Ongoing contract preparation
| RFQ No. 1209-21 One (1) Lot Peptone Water Culture Media 9btls/Tryptone Glucose Extract Agar Culture Media, 10btls | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Oct. 26-29, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 150000 | 150000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1035-21 Six (6) samples Testing Services | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Oct. 26-29, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 54000 | 54000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1212-21 Twenty Five (25) kgs Antimicrobial Finishing Formulation for textiles | [19 empty] | RDD | NO | Shopping | N/A | Nov. 2-9, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 200000 | 200000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1213-21 Twenty Five (25) kgs Anti-viral Finishing Formulation for textiles | [19 empty] | RDD | NO | Shopping | N/A | Nov. 2-9, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 75000 | 75000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1253-21 Two (2) sets Electronic Weighing Scale | [19 empty] | TSD | NO | Shopping | N/A | Nov. 8-15, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 240000 | 240000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1251-21 One (1) Set Manual Silver Wrap Block with Counter/ One (1) set Yarn Wrap Reel | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Nov. 8-15, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 150000 | 150000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ no. 1252-21 Five (5) Sets 3 Ton Air Conditioner | [19 empty] | TSD | NO | Shopping | N/A | Nov. 8-15, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 750000 | 750000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1243-21 (150kgs) Abaca Fiber (S2 Grade) | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Nov.11-15, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 57000 | 57000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1263-21 One (1) lot AATCC Microorganisms | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Nov. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 120000 | 120000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1280-21 Five (5) Units Laptop | [19 empty] | PICTS | NO | Shopping | N/A | Nov. 15-19, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 225000 | 225000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1279-21 Six (6) Units Desktop Computer | [19 empty] | PICTS | NO | Shopping | N/A | Nov. 15-19, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 240000 | 240000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1244-21 (150kgs) Decorticated pineapple fiber (unbrushed) | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Nov. 15-19, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 135000 | 135000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1266-21 One (1) Lot Supply and Delivery of Prepaid Cards | [19 empty] | TSD | NO | Shopping | N/A | Nov.16-19, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 63800 | 63800 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1316-21 One (1) Lot Renovation of the PTRI Testing Laboratory (Face Mask Testing) | [19 empty] | TSD | NO | Shopping | N/A | Nov.16-19, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 759885.78 | 759885.78 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Repair and Renovation of the TBI 2nd Floor Laboratory (NatDyes) | [19 empty] | RDD | NO | Shopping | N/A | Nov. 16-22, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 664500 | 664500 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1346-21 One (1) Lot Glassware | [19 empty] | TSD | NO | Shopping | N/A | Nov.16-19, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 100000 | 100000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1336-21 One (1) Lot Latest version of ASTM Standard Test Methods | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Nov.16-22, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 86000 | 86000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1375-21 Thirty (30 )samples Scanning Electron Microscope | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Nov. 17-21, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 60000 | 60000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1379-21 One (1) Lot Nuclear Magnetic Resonance (NMR) | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Nov. 17-19, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 100000 | 100000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1400-21 One (1) Lot laptop Computer with accessories and software | [19 empty] | RDD | NO | Shopping | N/A | Nov. 17-19, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 130000 | 130000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1389-21 One (1) Lot Annual Subscription of Image and Video Editing Software | [19 empty] | TIPS | NO | Shopping | N/A | Nov. 17-19, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 140000 | 140000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1350-21 200 drums OTES/ 200 drums TEOS | [19 empty] | RDD | NO | Shopping | N/A | Nov. 17-23, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 400000 | 400000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Bamboo Extraction Machine | [19 empty] | RDD | NO | Competitive Bidding | 2021-11-11 | Nov.18, 2021 | 2021-11-25 | 2021-12-09 | 2021-12-09 | 2021-12-09 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 1200000 | 0 | 1200000 |  |  |  | COA/PCCI | 2021-11-18 | 2021-11-18 | 2021-11-18 | 2021-11-18 | N/A | N/A
| One (1) Lot Sound Insulation Analyzer | [19 empty] | RDD | NO | Competitive Bidding | 2021-10-20 | Oct. 26, 2021 | 2021-11-02 | 2021-11-16 | 2021-11-16 | 2021-11-16 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 0 | 0 | 0 |  |  |  | COA/PCCI | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-10-25 | N/A | N/A | FAILED BID.
| One (1) Lot Sound Insulation Analyzer | [19 empty] | RDD | NO | Competitive Bidding | N/A | Nov.18, 2021 | 2021-11-25 | 2021-12-09 | 2021-12-09 | 2021-12-09 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 7800000 | 0 | 7800000 |  |  |  | COA/PCCI | 2021-11-18 | 2021-11-18 | 2021-11-18 | 2021-11-18 | N/A | N/A
| Four (4) Lots Bench Scale Degumming Equipment | [19 empty] | RDD | NO | Competitive Bidding | 2021-11-16 | Nov.18, 2021 | 2021-12-02 | 2021-12-14 | 2021-12-14 | 2021-12-14 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 1800000 | 0 | 1800000 |  |  |  | COA/PCCI | 2021-11-19 | 2021-11-19 | 2021-11-19 | 2021-11-19 | N/A | N/A
| One (1) Lot Precision Environmental Control System | [19 empty] | TSD | NO | Competitive Bidding | 2021-11-16 | Nov.18, 2021 | 2021-11-25 | 2021-12-09 | 2021-12-09 | 2021-12-09 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 0 | 0 | 0 |  |  |  | COA/PCCI | 2021-11-18 | 2021-11-18 | 2021-11-18 | 2021-11-18 | N/A | N/A
| RFQ No. 1260-21 One (1) Lot Laboratory PPE for Hands and Feet | [19 empty] | TSD | NO | Shopping | N/A | Nov. 22-29, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 60000 | 60000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1416-21 One (1) Lot Interoffice Communication System | [19 empty] | TSD | NO | Shopping | N/A | Nov. 24-26, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 350000 | 350000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1229-21 One (1) Lot Saboraud Dextrose Agar Culture Media (15btls) Saboraud Dextrose Broth Culture media (12btls) | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Nov. 24-26, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 120000 | 120000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1230-21 One (1) Lot Tryptic Soy Agar Culture Media (15btls) Saboraud Dextrose Broth Culture Media (12btls) | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Nov. 24-26, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 70000 | 70000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1413-21 One (1) Lot Microbiology Auxilliary Equipment | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Nov. 24-26, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 1000000 | 1000000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1480-21, 6,000 kgs Cotton Fibers | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Dec. 1- 6, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 780000 | 780000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1440-21 One (1) Lot Repairs and Renovation of Conditioning Room (5th Flr) | [19 empty] | RDD | NO | Shopping | N/A | Dec. 1-3, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 55500 | 55500 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1501-21 Three (3) Units Laptop with accessories and compatible software | [19 empty] | RDD | NO | Shopping | N/A | Dec. 7-10, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 300000 | 300000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1523-21 One (1) bale Polyester Staple Fiber | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Dec. 7-10, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 215000 | 215000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1550-21 13 carboys Acetic Acid | [19 empty] | TSD | NO | Shopping | N/A | Dec. 10-16, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 72800 | 72800 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1481-21 Two (2) Lots Decorticating Machine | [19 empty] | RDD | NO | Shopping | N/A | Dec. 10-16, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 250000 | 250000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1479-21 Four (4) Units Hydro Extractor | [19 empty] | RDD | NO | Shopping | N/A | Dec. 10-16, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 80000 | 80000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Production of High Definition Audio-Visual Promotional Videos for the DOST-PTRI Medical Textile Testing Center | [19 empty] | TSD | NO | Shopping | N/A | Dec. 10-16, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 160000 | 160000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot: One (1) Set Integrated Blow-Card with 40pcs sliver cans and laptop; One (1) Set Double Feed Draw Frame Machine with 100 pcs sliver cans; One (1) set 24 spindle Roving Machine.... | [19 empty] | TSD | NO | Competitive Bidding | 2021-11-09 | Nov. 17, 2021 | 2021-11-24 | Dec. 7, 2021 | Dec. 7, 2021 | Dec. 7, 2021 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 0 | 0 | 0 |  |  |  | COA/PCCI | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-17 | N/A | N/A | FAILED BID.
| One (1) Lot: One (1) Set Integrated Blow-Card with 40pcs sliver cans and laptop; One (1) Set Double Feed Draw Frame Machine with 100 pcs sliver cans; One (1) set 24 spindle Roving Machine.... | [19 empty] | TSD | NO | Competitive Bidding | N/A | Dec.14, 2021 | 2021-12-21 | Jan. 4, 2022 | Jan. 4, 2022 | Jan. 4, 2022 | 2022-01-11 |  | N/A | N/A | N/A | N/A | N/A | GoP | 23900000 | 0 | 23900000 |  |  |  | COA/PCCI | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-14 | N/A | N/A
| One (1) Lot Fiber Pre-Treatment Facility (Rebidding) | [19 empty] | RDD | NO | Competitive Bidding | N/A | Dec. 15, 2021 | 2021-12-22 | Jan. 4, 2022 | Jan. 4, 2022 | Jan. 4, 2022 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 4340000 | 0 | 4340000 |  |  |  | COA/PCCI | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-15 | N/A | N/A | FAILED BID.
| Two (2) Lots Mechanical Softening Machine (Rebidding) | [19 empty] | RDD | NO | Competitive Bidding | N/A | Dec. 15, 2021 | 2021-12-22 | Jan. 4, 2022 | Jan. 4, 2022 | Jan. 4, 2022 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 3000000 | 0 | 3000000 |  |  |  | COA/PCCI | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-15 | N/A | N/A | FAILED BID.
| Two (2) Lots Hard Fiber Opener | [19 empty] | RDD | NO | Competitive Bidding | 2021-11-16 | Nov. 18, 2021 | 2021-11-26 | 2021-12-14 | 2021-12-14 | 2021-12-14 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 1200000 | 0 | 1200000 |  |  |  | COA/PCCI | 2021-11-19 | 2021-11-19 | 2021-11-19 | 2021-11-19 | N/A | N/A
| One (1) Lot Bamboo Slatting Machine | [19 empty] | RDD | NO | Competitive Bidding | 2021-11-16 | Nov. 18, 2021 | 2021-11-26 | 2021-12-14 | 2021-12-14 | 2021-12-14 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 1200000 | 0 | 1200000 |  |  |  | COA/PCCI | 2021-11-19 | 2021-11-19 | 2021-11-19 | 2021-11-19 | N/A | N/A | FAILED BID.
| RFQ No. 1614-21 Five (5) Units Laptop | [19 empty] | PICTS | NO | Shopping | N/A | Dec. 20-22, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 250000 | 250000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1621-21 One (1) Lot Precision Environmental Control System | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Dec. 23-27, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 1000000 | 1000000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1618-21 Eight (8) Samples Nonwoven Stiffness Testing (ASTM 5733) | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Dec. 24-27, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 57568 | 57568 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1619-21 Eight (8) samples Nonwoven Air Permeabillity (ASTM D737) | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Dec. 24-27, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 83776 | 83776 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 103-21 Two (2) Units Distilling Apparatus | [19 empty] | RDD | NO | Shopping | N/A | Feb. 18-26, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 900000 | 900000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A
| 4,500 kgs CVC 20/1 (60% combed cotton, 40% polyester) | [20 empty] | NO | Direct Contracting | N/A |  | N/A | N/A | N/A | N/A | N/A | 2021-03-02 | 2021-03-02 | N/A | N/A | N/A | N/A | GoP | 0 | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 156-21 (100kgs) Pineapple Fiber (unbrushed) | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Mar. 9-16, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 71700 | 71700 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 196-21 One (1) Lot Monthly Subscription of 30MBps Internet Service (Burstable ) 9/24 | [19 empty] | PICTS | NO | Shopping | N/A | Mar. 15-22, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 99000 | 99000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Unit Temperature and Humidity Chamber | [19 empty] | TSD | NO | Competitive Bidding | N/A | Mar. 16-25, 2021 | 2021-03-24 | 2021-04-07 | 2021-04-07 | 2021-04-07 | 2021-06-09 | 2021-07-08 | 2021-07-08 | 2021-08-05 | 2021-08-05 | N/A | N/A | GoP | 1600000 | 0 | 1600000 |  |  |  | COA/PCCI | 2021-03-16 | 2021-03-16 | 2021-03-16 | 2021-03-16 | N/A | N/A
| One (1) Unit Flex Tester | [19 empty] | TSD | NO | Competitive Bidding | N/A | Mar. 16-25, 2021 | 2021-03-24 | 2021-04-07 | 2021-04-07 | 2021-04-07 | 2021-06-09 | 2021-07-16 | 2021-07-16 | 2021-08-05 | 2021-08-09 | N/A | N/A | GoP | 2000000 | 0 | 2000000 |  |  |  | COA/PCCI | 2021-03-16 | 2021-03-16 | 2021-03-16 | 2021-03-16 | N/A | N/A
| One (1) Unit Microbial Penetration Test System | [19 empty] | TSD | NO | Competitive Bidding | N/A | Mar. 16-25, 2021 | 2021-03-24 | 2021-04-07 | 2021-04-07 | 2021-04-07 | 2021-06-09 | 2021-07-16 | 2021-07-16 | 2021-08-05 | 2021-08-09 | N/A | N/A | GoP | 3500000 | 0 | 3500000 |  |  |  | COA/PCCI | 2021-03-16 | 2021-03-16 | 2021-03-16 | 2021-03-16 | N/A | N/A
| One (1) Lot Particle Filtration Efficiency Test System | [19 empty] | TSD | NO | Competitive Bidding | N/A | Mar. 16-25, 2021 | 2021-03-24 | 2021-04-07 | 2021-04-07 | 2021-04-07 | 2021-06-10 | 2021-08-04 | 2021-08-04 | 2021-08-23 | 2021-08-23 | N/A | N/A | GoP | 14000000 | 0 | 14000000 |  |  |  | COA/PCCI | 2021-03-16 | 2021-03-16 | 2021-03-16 | 2021-03-16 | N/A | N/A
| One (1) Unit Handheld Colorimeter | [19 empty] | RDD | NO | Competitive Bidding | N/A | Apr. 22-May 3, 2021 | 2021-04-30 | 2021-05-12 | 2021-05-12 | 2021-05-12 | NA | 2021-05-26 | 2021-05-26 | 2021-07-30 | 2021-07-30 | N/A | N/A | GoP | 1200000 | 0 | 1200000 |  |  |  | COA/PCCI | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 | N/A | N/A
| RFQ No. 450-21 (48 boxes) Nitrile Gloves, various sizes | [19 empty] | TSD | NO | Shopping | N/A | May 3-10, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 67200 | 67200 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 381-21 2,000 pcs Paper cones | [19 empty] | RDD | NO | Shopping | N/A | May 3-10, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 116000 | 116000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 2104-434 100 gallons Alcohol 70% Solution | [19 empty] | TSD | NO | Shopping | N/A | May 3-10, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 75000 | 75000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 460-21 (R) Various Toner Cart for HP | [19 empty] | TSD | NO | Shopping | N/A | May 6-13, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 62000 | 62000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 506-21 150 meters Woven Fabric (100% Polyester) | [19 empty] | RDD | NO | Shopping | N/A | May 14-21, 2021 | N/A | N/A | N/A | N/A | N/A | 2021-08-03 | 2021-08-03 | 2021-08-03 | 2021-08-06 | N/A | N/A | GoP | 52500 | 52500 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Laboratory High Temperature Dyeing/ Degumming Machine | [19 empty] | RDD | NO | Competitive Bidding | 2021-05-27 | June 18-24,2021 | 2021-07-02 | July 14, 2021 | July 14, 2021 | July 14, 2021 | N/A | 2021-08-19 | 2021-08-19 | 2021-09-20 | 2021-09-20 | N/A | N/A | GoP | 2200000 | 0 | 2200000 |  |  |  | COA/PCCI | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-06-21 | N/A | N/A
| One (1) Lot Laboratory Preneedling Machine | [19 empty] | RDD | NO | Competitive Bidding | 2021-05-27 | June 18-24,2021 | 2021-06-25 | July 7, 2021 | July 7, 2021 | July 7, 2021 | N/A | 2021-08-19 | 2021-08-19 | 2021-09-15 | 2021-09-15 | N/A | N/A | GoP | 3000000 | 0 | 3000000 |  |  |  | COA/PCCI | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-06-21 | N/A | N/A
| One (1) Lot Spectrofluometer | [19 empty] | RDD | NO | Competitive Bidding | 2021-05-27 | June 18-24,2021 | 2021-06-25 | July 7, 2021 | July 7, 2021 | July 7, 2021 | N/A | 2021-07-28 | 2021-07-28 | 2021-09-13 | 2021-09-13 | N/A | N/A | GoP | 8000000 | 0 | 8000000 |  |  |  | COA/PCCI | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-06-21 | N/A | N/A
| One (1) Unit Bursting Strength Tester | [19 empty] | TSD | NO | Competitive Bidding | N/A | June 18-24,2021 | 2021-06-25 | July 7, 2021 | July 7, 2021 | July 7, 2021 | N/A | 2021-08-25 | 2021-08-25 | 2021-09-13 | 2021-09-13 | N/A | N/A | GoP | 1600000 | 0 | 1600000 |  |  |  | COA/PCCI | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-06-21 | N/A | N/A
| RFQ No. 787-21 One (1) Bale Lyocell Fibers | [19 empty] | RDD | NO | Shopping | N/A | July 23-30, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 250000 | 250000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Unit Portable Near Infrared (NIR) with Cloud Storage and Software | [19 empty] | RDD | NO | Competitive Bidding | 2021-05-27 | July 27- August 2, 2021 | 2021-08-04 | Aug. 24, 2021 | Aug. 24, 2021 | Aug. 24, 2021 | N/A | Sept. 9, 2021 | Sept. 10, 2021 | N/A | N/A | N/A | N/A | GoP | 3000000 | 0 | 3000000 |  |  |  | COA/PCCI | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-07-27 | N/A | N/A
| RFQ no. 830-21 One (1) Unit Humidity Chamber | [19 empty] | RDD | NO | Shopping | N/A | Aug.3-10, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 1000000 | 1000000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 901-21 6 Units Monochrome Printer | [19 empty] | PICTS | NO | Shopping | N/A | Aug. 18-25, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 96000 | 96000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 914-21 One (1) Lot Vibrating Table | [19 empty] | RDD | NO | Shopping | N/A | Aug. 18-25, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 500000 | 500000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Textile Scanner | [19 empty] | RDD | NO | Competitive Bidding | 2021-08-16 | Aug. 24-30, 2021 | 2021-08-31 | Sept. 14, 2021 | Sept. 14, 2021 | Sept. 14, 2021 | Sept. 30, 2021 | 2021-10-14 | 2021-10-14 | 2021-11-11 | 2021-11-11 | N/A | N/A | GoP | 2747000 | 0 | 2747000 |  |  |  | COA/PCCI | 2021-08-23 | 2021-08-23 | 2021-08-23 | 2021-08-23 | N/A | N/A
| One (1) Lot Tensiometer | [19 empty] | TSD | NO | Competitive Bidding | N/A | Aug. 26-Sept. 1, 2021 | Sept. 2, 2021 | Sept. 14, 2021 | Sept. 14, 2021 | Sept. 14, 2021 | N/A | 2021-10-05 | 2021-10-05 | 2021-11-02 | 2021-11-02 | N/A | N/A | GoP | 1369200 | 0 | 1369200 |  |  |  | COA/PCCI | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-24 | N/A | N/A
| RFQ No. 935-21 One (1) Lot Troubleshooting of Middle Speed Needle Punching Machine | [19 empty] | RDD | NO | Shopping | N/A | Sept. 1-8, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 100000 | 100000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Sweating Guarded Hotplate | [19 empty] | TSD | NO | Competitive Bidding | 2021-08-23 | Sept. 7-13, 2021 | Sept. 14, 2021 | Sept. 27, 2021 | Sept. 27, 2021 | Sept. 27, 2021 | N/A | 2021-10-15 | 2021-10-15 | 2021-11-05 | 2021-11-05 | N/A | N/A | GoP | 6650000 | 0 | 6650000 |  |  |  | COA/PCCI | Sept. 7, 2021 | Sept. 7, 2021 | Sept. 7, 2021 | Sept. 7, 2021 | N/A | N/A
| One (1) Lot Fourier Transform Infrared Spectroscopy System | [19 empty] | TSD | NO | Competitive Bidding | Sept. 1, 2021 | Sept. 7-13, 2021 | Sept. 14, 2021 | Sept. 27, 2021 | Sept. 27, 2021 | Sept. 27, 2021 | 2021-10-28 | 2021-11-05 | 2021-11-05 | 2021-11-18 | 2021-11-18 | N/A | N/A | GoP | 2000000 | 0 | 2000000 |  |  |  | COA/PCCI | Sept. 7, 2021 | Sept. 7, 2021 | Sept. 7, 2021 | Sept. 7, 2021 | N/A | N/A
| One (1) Lot Universal Testing Machine, 5kN | [19 empty] | TSD | NO | Competitive Bidding | Sept. 1, 2021 | Sept. 7-13, 2021 | Sept. 14, 2021 | Sept. 27, 2021 | Sept. 27, 2021 | Sept. 27, 2021 | N/A | 2021-10-28 | 2021-10-28 | 2021-11-12 | 2021-11-12 | N/A | N/A | GoP | 4600000 | 0 | 4600000 |  |  |  | COA/PCCI | Sept. 7, 2021 | Sept. 7, 2021 | Sept. 7, 2021 | Sept. 7, 2021 | N/A | N/A
| One (1) Lot Universal Testing Machine, 10kN | [19 empty] | TSD | NO | Competitive Bidding | Sept. 1, 2021 | Sept. 7-13, 2021 | Sept. 14, 2021 | Sept. 27, 2021 | Sept. 27, 2021 | Sept. 27, 2021 | N/A | 2021-10-28 | 2021-10-28 | 2021-11-12 | 2021-11-12 | N/A | N/A | GoP | 5500000 | 0 | 5500000 |  |  |  | COA/PCCI | Sept. 7, 2021 | Sept. 7, 2021 | Sept. 7, 2021 | Sept. 7, 2021 | N/A | N/A
| RFQ No. 1070-21 (R) One (1) Lot Videoconferencing Solution | [19 empty] | PICTS | NO | Shopping | N/A | Sept. 20-27, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 300000 | 0 | 300000 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Bamboo Extraction Machine | [19 empty] | RDD | NO | Competitive Bidding | N/A | June 18, 2021 | 2021-07-02 | 2021-07-14 | 2021-07-14 | 2021-07-14 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 0 | 0 | 0 |  |  |  | COA/PCCI | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-06-21 | N/A | N/A | FAILED BID.
| One (1) Lot Bamboo Extraction Machine | [19 empty] | RDD | NO | Competitive Bidding | N/A | June 18, 2021 | 2021-08-04 | 2021-08-24 | 2021-08-24 | 2021-08-24 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 0 | 0 | 0 |  |  |  | COA/PCCI | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-07-27 | N/A | N/A | FAILED BID.
| One (1) Lot Bamboo Extraction Machine | [19 empty] | RDD | NO | NP-53.1 Two Failed Biddings | N/A | Sept. 28-Oct.4, 2021 | Oct 5, 2021 | Oct. 13, 2021 | Oct. 13, 2021 | Oct. 13, 2021 | 2021-11-04 |  | N/A | N/A | N/A | N/A | N/A | GoP | 1200000 | 0 | 1200000 |  |  |  | COA/PCCI | Sept. 29, 2021 | Sept. 29, 2021 | Sept. 29, 2021 | Sept. 29, 2021 | N/A | N/A
| One (1) Lot Distilling Apparatus | [19 empty] | RDD | NO | Competitive Bidding | N/A | June 18, 2021 | 2021-06-25 | 2021-07-07 | 2021-07-07 | 2021-07-07 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 0 | 0 | 0 |  |  |  | COA/PCCI | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-06-21 | N/A | N/A | FAILED BID.
| One (1) Lot Distilling Apparatus | [19 empty] | RDD | NO | NP-53.1 Two Failed Biddings | N/A | Oct. 5-11, 2021 | 2021-10-13 | Oct. 26, 2021 | Oct. 26, 2021 | Oct. 26, 2021 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 1200000 | 0 | 1200000 |  |  |  | COA/PCCI | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2021-10-04 | N/A | N/A
| One (1) Lot Distilling Apparatus | [19 empty] | RDD | NO | Competitive Bidding | N/A | July 27, 2021 | 2021-08-04 | 2021-08-24 | 2021-08-24 | 2021-08-24 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 0 | 0 | 0 |  |  |  | COA/PCCI | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-07-27 | N/A | N/A | FAILED BID.
| RFQ No. 1111-21 (R) One (1) Unit Laptop Computer with Accessories and Software | [19 empty] | RDD | NO | Shopping | N/A | Oct. 6-8, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 130000 | 130000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1167-21 (R) One (1) Lot Repair and Renovation of Long Staple Fiber Pilot Plant Extension Ph. III | [19 empty] | RDD | NO | Shopping | N/A | Oct. 14-18, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 249451.6 | 249451.6 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Compression Molding Press | [19 empty] | RDD | NO | Competitive Bidding | 2021-07-21 | Aug. 11, 2021 | 2021-08-18 | 2021-08-31 | 2021-08-31 | 2021-08-31 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 0 | 0 | 0 |  |  |  | COA/PCCI | 2021-08-11 | 2021-08-11 | 2021-08-11 | 2021-08-11 | N/A | N/A | FAILED BID.
| One (1) Lot Compression Molding Press | [19 empty] | RDD | NO | Competitive Bidding | N/A | Sept. 21, 2021 | Sept. 28, 2021 | 2021-10-12 | 2021-10-12 | 2021-10-12 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 0 | 0 | 0 |  |  |  | COA/PCCI | Sept. 21, 2021 | Sept. 21, 2021 | Sept. 21, 2021 | Sept. 21, 2021 | N/A | N/A | FAILED BID.
| One (1) Lot Compression Molding Press | [19 empty] | RDD | NO | NP-53.1 Two Failed Biddings | N/A | Oct. 19-25, 2021 | 2021-10-26 | Nov. 5, 2021 | Nov. 5, 2021 | Nov. 5, 2021 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 5000000 | 0 | 5000000 |  |  |  | COA/PCCI | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-10-20 | N/A | N/A
| One (1) Lot Multi-Year Janitorial Services for the PTRI Main Office, Bicutan and Technology Center, Misamis Oriental | [19 empty] | FAD | NO | Competitive Bidding | Sept. 1, 2021 | Oct. 20-27, 2021 | 2021-10-27 | Nov 9, 2021 | Nov 9, 2021 | Nov 9, 2021 | 2021-11-18 |  | N/A | N/A | N/A | N/A | N/A | GoP | 1744000 | 0 | 1744000 |  |  |  | COA/PCCI | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-10-20 | N/A | N/A
| One (1) Lot Renovation of the PTRI Testing Laboratory | [19 empty] | TSD | NO | Competitive Bidding | 2021-10-26 | Oct. 29-Nov. 4, 2021 | 2021-11-05 | Nov. 17, 2021 | Nov. 17, 2021 | Nov. 17, 2021 | 2021-12-10 |  | N/A | N/A | N/A | N/A | N/A | GoP | 5700000 | 0 | 5700000 |  |  |  | COA/PCCI | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-10-28 | N/A | N/A
| One (1) Lot Shotcrete Machine | [19 empty] | RDD | NO | Competitive Bidding | 2021-07-21 | Aug. 11, 2021 | 2021-08-18 | 2021-08-31 | 2021-08-31 | 2021-08-31 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 0 | 0 | 0 |  |  |  | COA/PCCI | 2021-08-11 | 2021-08-11 | 2021-08-11 | 2021-08-11 | N/A | N/A | FAILED BID.
| One (1) Lot Shotcrete Machine | [19 empty] | RDD | NO | Competitive Bidding | N/A | Sept. 21, 2021 | Sept. 28, 2021 | 2021-10-12 | 2021-10-12 | 2021-10-12 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 0 | 0 | 0 |  |  |  | COA/PCCI | Sept. 21, 2021 | Sept. 21, 2021 | Sept. 21, 2021 | Sept. 21, 2021 | N/A | N/A | FAILED BID.
| One (1) Lot Shotcrete Machine | [19 empty] | RDD | NO | NP-53.1 Two Failed Biddings | N/A | Oct. 29-Nov. 4, 2021 | 2021-11-05 | Nov. 15, 2021 | Nov. 15, 2021 | Nov. 15, 2021 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 1500000 | 0 | 1500000 |  |  |  | COA/PCCI | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-10-28 | N/A | N/A
| RFQ No. 1218-21 One (1) Lot Transport Service (PTRI to ISAT-U, Miagao, Iloilo and vice versa) | [19 empty] | TSD | NO | Shopping | N/A | Nov. 2-4, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 170000 | 170000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1295-21 One (1) Unit Color Viewing Cabinet | [19 empty] | RDD | NO | NP-53.9 - Small Value Procurement | N/A | Nov. 11-17, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 500000 | 500000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1281-21 One (1) Lot Server (Tower-Type) | [19 empty] | PICTS | NO | Shopping | N/A | Nov. 15-19, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 200000 | 200000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| RFQ No. 1262-21 One (1) Lot PPE Testing | [19 empty] | TSD | NO | NP-53.9 - Small Value Procurement | N/A | Nov. 16-19, 2021 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 750000 | 750000 | 0 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
| One (1) Lot Laboratory Coating/Laminating Machine | [19 empty] | RDD | NO | Competitive Bidding | 2021-11-02 | Nov. 16-22, 2021 | 2021-11-23 | Dec. 6, 2021 | Dec. 6, 2021 | Dec. 6, 2021 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 2000000 | 0 | 2000000 |  |  |  | COA/PCCI | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2021-11-16 | N/A | N/A
| One (1) Lot Indigo Dyeing Machine | [19 empty] | RDD | NO | Competitive Bidding | 2021-11-11 | Nov. 16-22, 2021 | 2021-11-23 | Dec. 6, 2021 | Dec. 6, 2021 | Dec. 6, 2021 | 2021-12-15 |  | N/A | N/A | N/A | N/A | N/A | GoP | 1500000 | 0 | 1500000 |  |  |  | COA/PCCI | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2021-11-16 | N/A | N/A
| One (1) Lot Laboratory Scale Wetlaid Line | [19 empty] | RDD | NO | Competitive Bidding | 2021-11-02 | Nov. 16-22, 2021 | 2021-11-23 | Dec. 6, 2021 | Dec. 6, 2021 | Dec. 6, 2021 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 22000000 | 0 | 22000000 |  |  |  | COA/PCCI | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2021-11-16 | N/A | N/A
| Two (2) Lots Fiber Cutting Machine | [19 empty] | RDD | NO | Competitive Bidding | 2021-11-23 | Nov. 25, 2021 | 2021-12-02 | 2021-12-14 | 2021-12-14 | 2021-12-14 | N/A |  | N/A | N/A | N/A | N/A | N/A | GoP | 0 | [5 empty] | COA/PCCI | N/A | N/A | N/A | N/A | N/A | N/A
0
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 197334993.16
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | MARILOU G. AGUSTIN | [10 empty] | JULIUS L. LEAÑO, JR.,Ph.D. | [10 empty] | CELIA B. ELUMBA
[21 empty] | BAC Secretariat | [10 empty] | BAC Chairperson | [10 empty] | Head of the Procuring Entity

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement